SUHUM MUNICIPAL ASSEMBLY

Office of the Municipal Administration

P. O. Box 186

Tel: 0858-22363

Suhum.

15TH November, 2024

Office of the Municipal Administration

P. O. Box 186

Tel: 0858-22363

Suhum.

15TH November, 2024

In case of reply, the

Number and date of this

Letter should be quoted.

Our Ref--------------------

Your Ref-------------------

In case of reply, the

Number and date of this

Letter should be quoted.

Our Ref--------------------

Your Ref-------------------

`

SUBMISSION OF 2025 COMPOSITE ANNUAL ACTION PLAN.

I submit herewith the 2025 Annual Action Plan of the Suhum Municipal for your perusal and necessary action, please.

Thank You.

…………………………………….....................

ABDULAI ALIWU

(AG. MUNICIPAL COORDINATING DIRECTOR)

for: MUNICIPAL CHIEF EXECUTIVE

DISTRIBUTION

ALL HON. ASSEMBLY MEMBERS

SUHUM MUNICIPAL ASSEMBLY

ALL HEADS OF DEPARTMENTS/MPCU MEMBERS

SUHUM MUNICIPAL ASSEMBLY

Cc:

THE DIRECTOR

NATIONAL DEVELOPMENT PLANNING COMMISSION

ACCRA

ATTN.

REGIONAL ECONOMIC PLANNING OFFICER

SUHUM MUNICIPAL ASSEMBLY

2025 ANNUAL ACTION PLAN

OCTOBER, 2024

TABLE OF CONTENTS

Content……………………………………………………………………………………….Page

LIST OF ABBREVIATIONS	iii

CHAPTER ONE	Error! Bookmark not defined.

MUNICIPAL PROFILE	1

1.1 Introduction	1

1.2. Vision and Mission	3

1.3. District Development Goal	3

1.4 Annual Action Plan (2025)	4

# LIST OF ABBREVIATIONS

AIDS                     Acquired Immunodeficiency Syndrome

DACF                    District Assemblies Common Fund

DACF – RFG         District Assemblies Common Fund Responsive Factor Grant

DDF                       District Development Fund

GoG                        Government of Ghana

HIV                         Human Immunodeficiency Virus

IGF                          Internally Generated Fund

MHD                       Municipal Health Directorate

MP’sCF                   Member of Parliament’s Common Fund

MPCU                      Municipal Planning Coordinating Unit

MTDP                      Medium Term- Development Plan

PWDsCF                   Person Living with Disability Fund

SuMA                        Suhum Municipal Assembly

CCE                            Community Conversation Enhancement

RCC                          Reginal Coordinating Council

REPO                        Regional Economic Planning Officer

NDPC                       National Development Planning Commission

# MUNICIPAL PROFILE

## 1.1 Introduction

The 2025 Annual Action Plan is an extraction from the District Medium Term Development Plan (DMTDP-2022-2025).  It outlines prioritized programmes and activities that are intended to be implemented in 2025.  These programmes and their objectives constitute the road map in the municipality’s efforts to meet the District Medium Term Development Goal. The priority interventions for 2024 seek to address five main issues hindering the growth of   the municipality.  These include weak human resource base, low agricultural productivity, weak institutional capacity for service delivery, weak revenue mobilization and management capacity and poor infrastructure development. This plan is therefore the strategy to deal holistically with these problems and to provide a sustainable foundation for the accelerated development of the Municipality within the context of the National Development Strategy.

#### 1.1.1	Administration

The Suhum Municipality is one of the 33 administrative districts in the Eastern Region of Ghana. It used to be part of the defunct Suhum-Kraboa-Coaltar District until the Ayensuano District was carved out of it in July 2012 and Suhum elevated to a municipality status.

#### 1.1.2	LI Establishing the Municipality

It was established in July 2012 by Legislative Instrument (L.I.) 2048 and Suhum is the municipal capital.

#### 1.1.3	Population

The municipality has a population of 126,403 made up of 61,226 (48.7%) males and 65,177 (51.3%) females. This represents about three percent (3.4%) of the total population of the Eastern Region.  Also, 37.8 percent of the population are within the age group 0-14years (children), while 32.3 percent are youth (15-34 years) with 5.9 percent being aged (65+ years). According to MPCU projection based on 2010 population census.

#### 1.1.4	Municipal Economy

The economy of the municipality comprises agriculture, service, commerce and light industrial sectors. However, the details of these sectors are elaborated in the sections below.

##### 1.1.4.1	Agricultural Activities

More than half (57.8%) of households in the Municipality are engaged in agriculture. In terms of rural-urban distribution, the number of households engaged in agriculture in the rural areas (74.7%) is almost three times the number in the urban areas (25.3%). Most of the agricultural activities in the Municipality therefore take place in the rural areas.

Crop farming in the Municipality is very dominant in the rural areas. The number of households engaged in crop farming in the rural areas (77.4%) is about three times more than the number in urban areas (22.6%). Tree planting and livestock rearing is practiced by over 80 percent (80.6 and 81.2 percent respectively) of rural agricultural households which is four times higher than the number of agricultural households in the urban areas who are engaged in tree planting (19.4%) and livestock rearing (18.8%).

##### 1.1.4.2	Literacy and Education

In the Suhum Municipality, 85.1 percent of the population aged 11 years and older are literate. In all 19.5 percent of the population in the Municipality can read and write English only while 88.0 percent can read and write English and another language. The proportion of literate males to females is 91.6 percent and 79.5 percent respectively. However, the proportion of illiterate females (20.5%) is more than twice that of males (8.8%).

Six out of every ten (61.8%) persons who have attended school in the past have JSS/JHS or middle school as the highest level attained. The proportion of male tertiary graduates (5.0%) is more than twice the proportion of corresponding females (2.1%).

##### 1.1.4.3	Other Economic Characteristics- Sector and Activity

Generally, seven in ten (74.8%) persons aged 15 years and older in the Municipality are economically active. Among the economically active population, nine in ten persons (95.0%) are employed while 5.0 percent are not employed. There is not much gap between the proportion of males and females as 75.9 percent and 73.9 percent respectively are economically active.

Economic activity is lowest among the age group 15-19 years with 23 percent being economically active while 77 percent are not economically active. Among the economically active within that age group, 87.6% are employed with the rest (12.4%) not employed. Economic activity starts rising from the age group 20-24 years (70.3%) and peaks at 95.8 percent at 45-49 years and begins to fall consistently from the ages 50-54 (93.8%).

Agriculture, including forestry and fishing (37.7%) constitute the major industry of the employed population in the Suhum Municipality. Other major industries are wholesale and retail; repair of motor vehicles and motorcycles (21.9%), manufacturing (11.5%) and accommodation and food service activities (5.9%).

## 1.2. Vision and Mission

#### 1.2.1 Vision Statement

An environmentally friendly and economically viable Municipality with adequate and accessible amenities for the people to actualise their dreams and enjoy peaceful co-existence.

#### 1.2.2	Mission Statement

The Suhum Municipal assembly exists to constantly upgrade the quality of life of the people in the Municipality through the efficient mobilization and utilization of resources within an effective participatory local governance framework.

## 1.3. District Development Goal

The basic goal of the District Medium Term Plan (2022-2025) is to address the high levels of poverty in the district by creating the enabling environment for increased production and productivity and improvement in the delivery of basic services.

## 1.4 Annual Action Plan (2025)

For the Suhum municipal Assembly to achieve its objectives and realize its broad goal, with the aim to promoting the general well-being of the people, there are a number of programmes and projects to be undertake from January to December 2025. The table 1 below shows the various activities.

Table 1: Annual Action Plan, 2025

| S/N | Programme (PBB) | Sub-Programme (PBB) | Broad Activities | Location | Time frame Quarterly |  |  |  | Cost |  |  |  |  | Programme status |  | Implementing Institutions/Departments |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | DACF | DACF-RFG | IGF | Donor | New | On-going | Lead | Collab. |
| 1 | Management and Admin | Finance | Purchase of utility (water, electricity and data) | Suhum | * | * | * | * |  |  |  | 50,000.00 |  |  |  | Finance | Central Administration |
| 2 | Management and Admin | Finance | Provide for allowances, T&T, and grants | Suhum | * | * | * | * |  |  |  | 100,000.00 |  |  |  | Finance | Central Administration |
| 3 | Management and Admin | Finance | Purchase value books | Accra | * | * | * | * |  |  |  | 20,000.00 |  |  |  | Finance | Central Administration |
| 4 | Management and Admin | Finance | Provide for compensation, commission and casual laborers | Suhum | * | * | * | * |  |  |  | 350,000.00 |  |  |  | Finance | Central Administration |
| 5 | Management and Administration | General Administration | Donations / Official celebrations and scholarships | Suhum |  |  |  |  |  | 90,000.00 |  | 50,000.00 |  |  |  | Finance | Central Administration |
| 6 | Management and administration | General Administration | Payment of assembly members Ex- gratia |  |  |  |  |  |  |  |  | 80,000.00 |  |  |  | Finance | Central Administration |
| 7 | Management and Admin | General Administration | Procure office stationery and consumables | Suhum | * | * | * | * |  | 47,000.00 |  | 40,000.00 |  |  |  | Procurement | Central Adm. |
| 8 | Management and Admin | General Administration | Procure office equipment and logistics | Suhum | * | * | * | * |  | 90,000.00 |  |  |  |  |  | Procurement | Central Adm. |
| 9 | Management and Admin | General Administration | Provide logistical support to decentralized departments | Suhum | * | * | * | * |  | 30,000.00 |  |  |  |  |  | Finance | Central Adm. |
| 10 | Management and Admin | General Administration | Support Implementation of Agriculture Activities | Suhum | * | * | * | * |  | 30,000.00 |  |  |  |  |  | central | Agric. Dept |
| 11 | Management and Admin | General Administration | Provide for Hotel Accommodation for official guests | Suhum | * | * | * | * |  |  |  | 10,000.00 |  |  |  | Finance | Central Administration |
| 12 | Management and Admin | General Administration | Maintain, insurance& Repairs of official vehicles | Suhum | * | * | * | * |  | 100,000.00 |  | 50,000.00 |  |  |  | Transport | Central Administration |
| 13 | Management and Admin | General Administration | Support security operations | Suhum | * | * | * | * |  | 100,000.00 |  | 50,000.00 |  |  |  | Security agencies | Central Administration |
| 14 | Management and Admin | General Administration | Training programme for Assembly Drivers | Suhum | * | * | * | * |  |  |  | 6,000.00 |  |  |  | Transport | Central Administration |
| 15 | Management and Admin | Finance | Purchase of fuel and lubricants | Suhum | * | * | * | * |  | 91,000.00 |  | 70,000.00 |  |  |  | Transport | Central Administration |
| 16 | Management and Admin | General Administration | Maintenance /Rehabilitation/Repairs of office building | Suhum | * | * | * | * |  | 180,000.00 |  | 20,000.00 |  |  |  | MWD | Central Administration |
| 17 | Management and Admin | General Administration | Maintenance of furniture & fixtures | Suhum | * | * | * | * |  | 70,000.00 |  | 10,000.00 |  |  |  | Finance | Central Administration |
| 18 | Management and Admin | General Administration | Payment for various meeting (Tender Com, MPCU Sub.com, GA, ETC) | Suhum | * | * | * | * |  |  |  | 269,009.83 |  |  |  | Finance | SuMA |
| 19 | Management and Admin | Finance | Bank charges and payment of tax liability. | Suhum | * | * | * | * |  | 4,000.00 |  | 600.00 |  |  |  | Finance | SuMA |
| 20 | Management and Admin | Finance | Revenue improvement monitoring, education and sensitization of rate payers and data collection (RIAP) | Municipality wide | * | * | * | * |  | 15,000 |  | 40,000.00 |  |  |  | Finance/Budget | SuMA |
| 21 | Management and Admin | General Administration | Quarterly project monitoring | Municipality wide | * | * | * | * |  | 40,000.00 |  | 10,000.00 |  |  |  | MPCU | SuMA |
| 22 | Management and Admin | General Administration | Gazetting of FFR and Bye Laws | Suhum | * | * | * | * |  | 130,000 |  |  |  |  |  | Finance/Budget | SuMA |
| 23 | Management and Admin | General Administration | Public sensitization/Town hall meetings /meet the press | Municipality wide | * | * | * | * |  | 60,000.00 |  | 50,000.00 |  |  |  | MPCU | SuMA |
| 24 | Management and Admin | General Administration | Established Post | Suhum |  |  |  |  | 3,985,227.01 |  |  |  |  |  |  |  | Central Adm. |
| 25 | Management and Admin | General Administration | Furnishing of the 3 Zonal councils: curtains, furniture, printers, photocopiers, desktop computers, UPS, | Suhum | * | * | * | * |  | 50,0000.00 |  | 5,000.00 |  |  |  | MPCU | SuMA |
| 26 | Management and Admin | General Administration | Support to the smooth operations of the 3 Zonal councils | Suhum | * | * | * | * |  | 20,000 |  | 5,000.00 |  |  |  | MPCU | SuMA |
| 27 | Management and Admin | Planning, Budgeting and Co-ordination | Review 2025 budget and prepare 2026 composite budget and fee fixing document Asset and risk register | Suhum | * | * | * | * |  | 65,000.00 |  | 20,000 |  |  |  | MPCU | SuMA |
| 28 | Management and Admin | Planning, Budgeting and Co-ordination | Review of 2025 annual action plan and prepare medium-term plan 2026-2029 | Suhum | * | * | * | * |  | 95,000.00 |  |  |  |  |  | MPCU | SuMA |
| 29 | Management and Admin | General Administration | MP’s general contribution to community development | Municipality wide | * | * | * | * |  | 303,155.36 |  |  |  |  |  | MP | SuMA |
| 30 | Management and administration | Human resource management | Preparation of capacity building plans. | Suhum | * | * | * | * | 5,000.00 |  |  | 5,000.00 |  |  |  | HR | SuMA |
| 31 | Management and administration | Human resource management e | Preparation and submission of personnel updates and inputs | Suhum | * | * | * | * | 3,000.00 |  |  | 5,000.00 |  |  |  | HR | SuMA |
| 32 | Management and administration | Human resource management | Capacity building trainings | Suhum | * | * | * | * |  | 30,000.00 | 45,859.00 |  |  |  |  | HR |  |
| 33 | Economic Development | Agriculture Development | Monitoring, supervision and publicity on planned flagship projects. | Municipality wide | * | * | * | * | 10,000.00 |  |  | 5,000.00 | 1,000.00 |  |  | Agric Dep:t | SuMA |
| 34 | Economic Development | Agriculture Development | Servicing of RELC, review meetings, public forum, field day sessions and other extension services meeting | Municipality wide | * | * | * | * |  |  |  | 2,000.00 | 15,000.00 |  |  | Agric Dep:t | SuMA |
| 35 | Economic DEvelopment | Agriculture Development | Conduct Research Extension Farmer Linkage Committee | Municipality wide | * | * | * | * |  |  |  | 2,000.00 | 4,851.00 |  |  | Agric Dep:t | SuMA |
| 36 | Economic Development | Agriculture Development | Procure protective clothing and PPE | Municipality wide | * | * | * | * |  |  |  |  | 2,000.00 |  |  | Agric Dep:t | SuMA |
| 37 | Economic Development | Agriculture Development | Training of staff and farmers. | Municipality wide | * | * | * | * |  |  |  | 3,000.00 | 7,000.00 |  |  | Agric Dept. | SuMA |
| 38 | Economic Development | Agriculture Development | Train 15 women farmers on climate smart agriculture | Suhum Municipality | * | * | * | * |  |  |  |  | 1,000.00 |  |  | Agric Dept. | SuMA |
| 39 | Economic Development | Agriculture Development | Train 20 women in post-harvest management of fresh vegetables | Municipality wide | * | * | * | * |  |  |  |  | 2,000.00 |  |  | Agric Dept. | SuMA |
| 40 | Economic development | Agriculture Development | Municipal assembly monitor implementation of planned activities | Municipality wide | * | * | * | * | 1,000.00 |  |  | 2,000.00 | 2,400.00 |  |  | Agric Dept. | SuMA |
| 41 | Economic Development | Agriculture Development | Organize technical review meetings | Suhum municipality | * | * | * | * |  |  |  |  | 1,500.00 |  |  | Agric Dept. | SuMA |
| 42 | Economic Development | Agriculture Development | Train 15 women farmers in aflatoxin prevention and control in cereals and legumes | Suhum municipality | * | * | * | * |  |  |  |  | 1,500.00 |  |  | Agric Dept. | SuMA |
| 43 | Economic Development | Agriculture Development | Vaccinate animals against rabies and schedule diseases | Municipality wide | * | * | * | * |  |  |  | 3,000.00 |  |  |  | Agric Dept. | SuMA |
| 44 | Economic Development | Agriculture Development | Train technical staff to improve upon technical skills and knowledge (TECMAG). |  | * | * | * | * |  |  |  |  | 2,000.00 |  |  | Agric Dept. | SuMA |
| 45 | Economic Development | Agriculture development | MDA monitor implementation of Agricultural activities |  |  |  |  |  | 1,000.00 |  |  |  | 5,450.00 |  |  | Agric Dept. | SuMA |
| 46 | Economic Development | Agriculture development | Facilitate staff participation in training and workshops | Suhum Municipal | * | * | * | * |  |  |  |  | 2,200.00 |  |  | Agric Dept. | SuMA |
| 47 | Economic Development | Agriculture Development | Facilitate the participation of 5 women processors in satellite market activities | Municipality wide | * | * | * | * |  |  |  |  | 1,500.00 |  |  | Agric Dept. | SuMA |
| 48 | Economic Development | Agriculture Development | Celebration of 41ST farmer’s day. | Municipality wide | * | * | * | * |  | 80,000.00 |  | 20,000.00 |  |  |  | Agric Dep:t | SuMA |
| 49 | Economic Development | Agriculture Development | WIAD and LED activities | Municipality wide | * | * | * | * |  |  |  |  | 6,000.00 |  |  | Agric Dep:t | SuMA |
| 50 | Economic Development | Agriculture Development | Train 20 rearing for Food and Jobs Farmers on treatment against livestock disease | Sushum municipality | * | * | * | * | 1,000.00 |  |  |  | 1,000.00 |  |  | Agric Dep.t | SuMA |
| 51 | Economic Development | Agriculture Developmeng | Conduct market survey to determine prices of agricultural produce | Municipality wide | * | * | * | * |  |  |  |  | 1,760.00 |  |  | Agric Dep.t | SuMA |
| 52 | Economic Development | Agricultre Development | Conduct field demonstration and agricultural yield study. | Municipality wide | * | * | * | * |  |  |  |  | 2,110.00 |  |  | Agric Dept. | SuMA |
| 53 | Economic Development | Agriculture Development | Provide extension services to farmers through the conduct of home and farm visits. | Municipality wide | * | * | * | * | 2,680.00 |  |  |  | 25,700.00 |  |  | Agric Dept. | SuMA |
| 54 | Economic Development | Agriculture Development | Support to various flagship projects and contributions to national programmes. | Suhum | * | * | * | * |  | 100,000.00 |  |  | 19,247.63 |  |  | Agric Dep:t | SuMA |
| 55 | Economic Development | Agriculture Development | Support SMEs in agro-processing (Gari, Palm Oil and Vegetable production | Suhum |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 56 | Economic Development | Agriculture Development | Procure Start – Up Kits to support PWDS businesses | Suhum |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 57 | Economic Development | Statistics | Develop and update municipal data hub. | Suhum | * | * | * | * | 8,000.00 |  |  | 2,000.00 |  |  |  | SD | Central Adm. |
| 58 | Infrastructure | Physical Planning | Street Naming and Data collection | Suhum | * | * | * | * | 4,000.00 |  |  | 5,000.00 |  |  |  | PP | Central Amin |
| 59 | Infrastructure | Physical Planning | Prepare Spatial Development Framework (SDF) | Suhum | * | * | * | * |  | 20,000 |  |  |  |  |  | PP | Central Amin |
| 60 | Infrastructure Development | Physical planning | Inspection of site for permit/conduct public education on national building regulations of 1996 (Li Act 1630) | Suhum | * | * | * | * | 3,000.00 |  |  | 5,000.00 |  |  |  | PP | Central Admin |
| 61 | Infrastructure Delivery and Management | Infrastructure Development | Grading of selected Roads (9.66KM) | Suhum and environs | * | * | * | * |  |  |  |  |  |  |  | UR | Central Adm. |
| 62 | Infrastructure Delivery and management | Infrastructure development | Procurement of office equipment/ organize public education on planning schemes | Suhum and environs | * | * | * | * | 4,000.00 |  |  | 5,000.00 |  |  |  | Works department | Central Admin |
| 63 | Infrastructure and delivery management | Infrastructure development | Drilling of 10 No. Boreholes | Selected communities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 64 | Infrastructure Delivery and Management | Infrastructure Development | Desilting of streams and routine cleansing of open drains, kerbs and culverts in selected locations | Suhum | * | * | * | * |  | 81,000.00 |  |  |  |  |  | UR | Central Adm. |
| 65 | Economic development | Agriculture | Sensitization and vaccination of domestic animals/pets in the municipality. | Suhum | * | * | * | * |  |  |  | 10,000.00 |  |  |  | Agric Dept. | Central Adm. |
| 66 | Infrastructure Delivery and Management | Infrastructure Development | Conduct monitoring and inspections | Municipality wide | * | * | * | * | 5,000.00 |  |  | 2,000.00 |  |  |  | UR | Central Adm. |
| 67 | Infrastructure Delivery and Management | Infrastructure Development | Spatial Planning committee meetings and land use education | Municipality wide | * | * | * | * | 2,000.00 |  |  | 2,000.00 |  |  |  | PPD | Central Administration |
| 68 | Infrastructure Delivery and Management | Infrastructure Development | Inspection of site for permit/Conduct Public Education on National Building Regulations of 1996(L.I. 1630) | Municipality wide | * | * | * | * | 3,000.00 |  |  | 12,000.00 |  |  |  | PPD | Central Administration |
| 69 | Infrastructure and delivery management | Infrastructure Development | Complete payment and construction of 3 storey market complex (1st phase 16 unit) | Suhum Amponsah market | * | * | * | * |  | 800,000.00 |  |  |  |  |  | MWD | Central Administration |
| 70 | Infrastructure and delivery management | Infrastructure Development | Complete payment and construction of 3 storey market complex (2nd and 3rd phases 32 unit) | Suhum Amponsah market | * | * | * | * |  | 1,549,380.55 |  |  |  |  |  | MWD | Central Administration |
| 71 | Infrastructure and delivery management | Infrastructure Development | construction of 24Hour Economy Market (Multi-Purpose Story Lockable Stores | Suhum | * | * | * | * |  | 5,484,517.69 |  |  |  |  |  | MWD | Central Administration |
| 72 | Infrastructure and delivery management | Infrastructure Development | Complete payment and construction of 1No. police station with accommodation | Akorabo | * | * | * | * |  | 500,000 |  |  |  |  |  | MWD | Central Administration |
| 73 | Infrastructure and delivery management | Infrastructure Development | Support to community-initiated help projects | Municipality wide | * | * | * | * |  | 194,885.59 |  |  |  |  |  | MWD | Central Administration |
| 74 | Infrastructure and delivery management | Infrastructure Development | Refurbishment of Municipal Chief Executive’s official residency | Suhum | * | * | * | * |  | 60,000.00 |  | 40,000.00 |  |  |  | MWD | Central Administration |
| 75 | Infrastructure and delivery management | Infrastructure Development | Rehabilitation Works on Official Bungalows | Suhum | * | * | * | * |  | 200,000.00 |  | 40,000.00 |  |  |  | MWD | Central Administration |
| 78 | Infrastructure and delivery management | Infrastructure Development | Renovation, Furnishing and Ugrade of PA-System of Conference Room Block | Ministries - Suhum | * | * | * | * |  | 211,348.00 |  |  |  |  |  | MWD | Central Administration |
| 79 | Infrastructure and delivery management | Infrastructure Development | Construction and furnishing of 3No. unit classroom block with office, stores, staff common room and furnishing with 66 No. mono desk for pupils. 3 No. cabinet and 10 No. teachers’ tables and chairs. | Suhum Methodist JHS | * | * | * | * |  |  | 480,000.00 |  |  |  |  | MWD | Central Administration |
| 80 | Infrastructure and delivery management | Infrastructure Development | Construction of 1No. 4-seater KVIP and urinal | Suhum Methodist JHS | * | * | * | * |  |  | 100,000.00 |  |  |  |  | MWD | Central Administration |
| 81 | Infrastructure and delivery management | Infrastructure Development | Routine inspection and supervision | Municipality wide | * | * | * | * |  |  |  | 5,000.00 |  |  |  | MWD | Central Administration |
| 82 | Infrastructure and delivery management | Infrastructure Development | Drill and Mechanize 1No. Borehole/Fire Hydrant with 10ft square double Slab, 28ft High Overhead Tank with 50mm diameter Galvanized Pipe Ladder fixed into Column, Drilling of 80-100m Well, Installation of Specified/Approved 3.0HP Pump with Accessories, Supply and installation of Water Tank. (2No. 5000 liters), Supply and installation of Switch Board and Connect to ECG Grid | Suhum- Fire Service Complex | * | * | * | * |  | 200,000 |  |  |  |  |  | MWD | Central Administration/GNFS |
| 83 | Infrastructure and delivery management | Infrastructure Development | Drill and Mechanize 1No. Borehole with 10ft square Slab, 28ft High Overhead Tank with 50mm diameter Galvanized Pipe Ladder fixed into Column, Drilling of 80-100m Well, Installation of Specified/Approved 2.5HP Pump with Accessories, Supply and installation of Water Tank. (5000 liters), Pipe Work Connections, Supply and installation of Switch Board with Separate Meter and Connect to ECG Grid | Suhum Residency Enclave | * | * | * | * |  | 150,000 |  |  |  |  |  | MWD | Central Administration |
| 84 | Infrastructure and delivery management | Infrastructure Development | Drill and Mechanize 5No. Institutional Boreholes with 8ft square Single Slab, 12ft High Overhead Tank, Drilling of 60-100m Well, Installation of Specified/Approved 2.0HP Pump with Accessories, Supply and installation of Water Tank. (4000 liters), Supply and installation of Switch Board with Separate Meters and Connect to ECG Grid | Akorabo CHPS Compound, Abenabo CHPS Compound, Adarkwa Primary School, Akorabo 3-Unit Classroom Block, Kokooso KG and Nursary | * | * | * | * |  | 500,000 |  |  |  |  |  | MWD | Central Administration |
| 85 | Infrastructure and delivery management | Infrastructure Development | Drill and Mechanize 8No. Boreholes with 8ft square Single Slab, 12ft High Overhead Tank, Drilling of 60-100m Well, Installation of Specified/Approved 2.0HP Pump with Accessories, Supply and installation of Water Tank. (4000 liters), Supply and installation of Switch Board with Separate Meters and Connect to ECG Grid | Odokum,Down Villa,Niifio,Ahafi,Dawn of Life,Kokosi Ase,Abenabo,Metemano | * | * | * | * |  | 800,000 |  |  |  |  |  | MWD | Central Administration |
| 86 | Infrastructure and delivery management | Infrastructure Development | Drill 10No. Boreholes (60-100m depth) with Hand Pump, Accessories and Platform Construction | Jato,Yokonor,AbominaNkatekwan | * | * | * | * |  | 500,000 |  |  |  |  |  | MWD | Central Administration |
| 87 | Infrastructure and delivery management | Infrastructure Development | Repair and Maintenance of 12No. Boreholes (Mechanized/ HandPump) | District-wide | * | * | * | * |  | 43,807.08 |  |  |  |  |  | MWD | Central Administration |
| 88 | Infrastructure and delivery management | Infrastructure Development | Purchase of printed material and stationery | Suhum | * | * | * | * |  |  |  | 5,000.00 |  |  |  | MWD | Central Administration |
| 89 | Infrastructure and delivery management | Infrastructure Development | Purchase of petty tools | Suhum | * | * | * | * |  |  |  | 2,000.00 |  |  |  | MWD | Central Administration |
| 90 | Infrastructure Delivery and Management | Infrastructure Development | Complete payment of 1No. 10-seater W/C Toilet | Omenako | * | * | * | * |  |  |  | 200,473.00 |  |  |  | MWD | Central Administration |
| 91 | Infrastructure Delivery and Management | Infrastructure Development | Complete payment of 1No. 10-seater W/C Toilet | Suhum Newtown | * | * | * | * |  |  |  | 20,746.35 |  |  |  | MWD | Central Administration. |
| 92 | Infrastructure and delivery management | Infrastructure Development | Complete reshaping and gravelling of selected roads | Municipality wide | * | * | * | * |  | 35,328.00 |  |  |  |  |  | MWD | Central Administration |
| 93 | Infrastructure and delivery management | Infrastructure Development | Construct a duty post for staff at cemetery | Suhum | * | * | * | * |  |  |  | 50,000.00 |  |  |  | MWD | Central Administration |
| 94 | Infrastructure and delivery management | Infrastructure Development | Rehabilitation of assembly store room | Suhum | * | * | * | * |  |  |  | 10,000.00 |  |  |  | MWD | Central Administration |
| 95 | Infrastructure and delivery management | Infrastructure Development | Complete ICT Installations and furnishing and Rehabilitation of Assembly Main Block | Suhum | * | * | * | * |  | 280,000 |  |  |  |  |  | MWD | Central Administration |
| 96 | Infrastructure and delivery management | Infrastructure Development | Support to the departmental activities and functioning. | Suhum | * | * | * | * | 15,000.00 |  |  |  |  |  |  | MWD | Central Administration |
| 97 | Infrastructure Delivery and Management | Infrastructure Development | Rehabilitation of streetlight and street naming and data collection. | Municipality wide | * | * | * | * | 4,00000 | 80,000.00 |  | 35,000.00 |  |  |  | MWD | Central Administration |
| 98 | Infrastructure and delivery management | Infrastructure Development | Reshaping of roads | Hospital junction | * | * | * | * |  | 23,625.00 |  |  |  |  |  | MWD | Central Administration |
| 99 | Social Services Delivery | Education and Youth Development | Support to the organization of STMIE and SPAM | Municipality wide | * | * | * | * |  | 5,000.00 |  | 5,000.00 |  |  |  | GES | Central Adm. |
| 100 | Social Services Delivery | Education and Youth Development | Procure 90No. Octagon Tables and Chairs for KG Schools – Metal Fabrication | Municipality wide | * | * | * | * |  | 360,000.00 |  |  |  |  |  | GES | Central Adm. |
| 101 | Infrastructure and delivery management | Infrastructure Development | Completion of 1No. Toilet Facilities (20 seater)- MBDA | Kwabena Kumi |  |  |  |  |  | 100,000 |  |  |  |  |  | MWD | Central Administration |
| 102 | Infrastructure and delivery management | Infrastructure Development | Completion of 1No. Toilet Facilities 10 seater) - MBDA | Jato ( |  |  |  |  |  | 50,000 |  |  |  |  |  | MWD | Central Administration |
| 103 | Infrastructure and delivery management | Infrastructure Development | Completion of 1No. Toilet Facilities (10 seater)- MBDA | Akote |  |  |  |  |  | 50,000 |  |  |  |  |  | MWD | Central Administration |
| 104 | Infrastructure and delivery management | Infrastructure Development | Completion of 1No. Health Facility - MBDA | Kwabena Kumi |  |  |  |  |  | 200,000 |  |  |  |  |  | MWD | Central Administration |
| 105 | Infrastructure and delivery management | Infrastructure Development | Completion of Rehabilitation and Furnishing of Phi-beta ICT Center | Phi-beta ICT Center -Suhum |  |  |  |  |  | 150,122.00 |  |  |  |  |  | MWD | Central Administration |
| 106 | Social Services Delivery | Education and Youth Development | Procure 640No. Dual Desk for Public Primary Schools – Metal Fabrication | Municipality wide | * | * | * | * |  | 900,000.00 |  |  |  |  |  | GES | Central Adm. |
| 107 | Social Services Delivery | Education and Youth Development | Procure 720No. Mono Desk for Public JHS Schools – Metal Fabrication | Municipality wide | * | * | * | * |  | 780,000.00 |  |  |  |  |  | GES | Central Adm. |
| 108 | Social Services Delivery | Education and Youth Development | Procure 720No. Mono Desk for Public JHS Schools – Metal Fabrication | Municipality wide | * | * | * | * |  | 1530,807.07 |  |  |  |  |  | GES | Central Adm. |
| 109 | Social Services Delivery | Education and Youth Development | Servicing of Municipal Education oversight committee meetings | Suhum | * | * | * | * |  |  |  | 5,000.00 |  |  |  | GES | Central Administration |
| 110 | Social Services Delivery | Education and Youth Development | Provision of hygiene facilities in public schools | Municipality wide | * | * | * | * |  |  |  | 7,000.00 |  |  |  | GES | Central Adm. |
| 111 | Social Services Delivery | Education and Youth Development | Independence Day celebration | Suhum | * | * | * | * |  |  | 80,000.00 |  |  |  |  | GES | Central Adm. |
| 112 | Social Services Delivery | Education and Youth Development | Support to school enrolment drive | Municipality wide | * | * | * | * |  |  |  | 3,000.00 |  |  |  | GES | Central Adm. |
| 113 | Social Services Delivery | Education and Youth Development | Construction of 1No. 3-Unit Classroom Block with Ancillary Facilities | Suhum Krobom |  |  |  |  |  |  | 505,306.00 |  |  |  |  | GES | Central Adm. |
| 114 | Social Services Delivery | Education and Youth Development | Construction of 1No. 6-Unit Classroom Block with Ancillary Facilities | Praprababida-Sna |  |  |  |  |  |  | 850,000.00 |  |  |  |  | GES | Central Adm. |
| 115 | Social Services Delivery | Education and Youth Development | Rehabilitation of Municipal Education Director Bungalow | Suhum | * | * | * | * |  | 38,055.60 |  |  |  |  |  | GES | Central Adm. |
| 116 | Social Services Delivery | Education and Youth Development | Support to needy-but- brilliant students | Municipality wide | * | * | * | * |  | 77,954.24 |  |  |  |  |  | GES | Central Adm. |
| 117 | Social Services Delivery | Education and Youth Development | MP’s support to needy-but- brilliant students | Municipality wide | * | * | * | * |  | 20,000.00 |  |  |  |  |  | SUMA | Central Adm. |
| 118 | Social Services Delivery | Education and Youth Development | Construction of 1No. 6-seater W/C and mechanized boreholes at Suhum M/A Primary School | Suhum M/A primary school. | * | * | * | * |  |  | 60,000.00 |  |  |  |  | GES | Central Adm. |
| 119 | Social Services Delivery | Education and Youth Development | Construction of 1No. 6-unit classroom block with ancillary facilities | Abenabo | * | * | * | * |  |  | 600,000.00 |  |  |  |  | GES | Central Adm. |
| 120 | Social Services Delivery | Education and Youth Development | Purchase of cleaning materials/sanitation / Covid 19 items. | Suhum | * | * | * | * |  | 20,000.00 |  | 30,000.00 |  |  |  | GES | Central Adm. |
| 121 | Social Services Delivery | Education and Youth Development | Construction of 1No. 3-Unit Classroom Block with Office, Store, Staff Common Room, 2-Unit Urinal and 4- Seater W/C | Akorabo | * | * | * | * |  |  | 600,000.00 |  |  |  |  | GES | Central Adm. |
| 122 | Social Services Delivery | Education and Youth Development | Construction of 1No. 3-Unit Classroom Block with Office, Store, Staff Common Room, 2-Unit Urinal and 4- Seater W/C at Akorabo | Kokooso | * | * | * | * |  |  | 643,807.08 |  |  |  |  | GES | Central Adm. |
| 123 | Social Services Delivery | Health Delivery | Support to immunization and other public health outreach programmes | Municipality wide | * | * | * | * |  |  |  | 5,000.00 |  |  |  | GHS | Central Adm. |
| 124 | Social Services Delivery | Health Delivery | HIV/AIDS and roll back malaria programme | Municipaclity wide | * | * | * | * |  | 110,000 |  |  |  |  |  | GHS | Central Adm. |
| 125 | Social Services Delivery | Health Delivery | Organize municipal health committee meetings | Municipality wide | * | * | * | * |  |  |  | 5,000.00 |  |  |  | GHS | Central Adm. |
| 126 | Social Services Delivery | Health Delivery | Complete construction and payment for 1No. CHPS compound with nurses’ quarters and mechanized borehole | Asarekrom | * | * | * | * |  | 204,341.80 |  |  |  |  |  | GHS | Central Adm. |
| 127 | Social Services Delivery | Health Delivery | Construction and furnishing of 1No. CHPS Compound with Maternity Block, Septic Tank, Dispensary, O.P.D, Laboratory, Consulting Room, Recovery Room, Two Bedroom and Living Room Nurses Quarters | Akorabo | * | * | * | * |  | 1,096,903.54 |  |  |  |  |  | GHS | Central Adm. |
| 128 | Social Services Delivery | Health Delivery | Construction and Furnishing of 1No. CHPS Compound with Maternity Block, Septic Tank, Dispensary, O.P.D, Laboratory, Consulting Room, Recovery Room, Two Bedroom and Living Room Nurses Quarters at Abenabo | Abenabo | * | * | * | * |  | 1,096,903.54 |  |  |  |  |  | GHS | Central Adm. |
| 129 | Social Services Delivery | social welfare &comm. dev | Continue the registration and monitoring of PWD’s. | Municipality wide | * | * | * | * |  |  |  | 3,000.00 |  |  |  | Dep’t SWCD | Central Adm. |
| 130 | Social Services Delivery | social welfare &comm. dev | Support to PWDs, PWD meetings/Provision for Disability Fund and Sensitize PWDs on the Disability Act, 2006(Act 715) | Municipality wide | * | * | * | * |  | 129,923.72 |  |  |  |  |  | Dep’t SWCD | Central Adm. |
| 131 | Social Services Delivery | social welfare &comm. dev | Provide funds for monitoring visits to Day Care Centers, carry out routine visits to Court and Provide funds for Monitoring activities of parents and children as required by the children’s Act of 1998(Act 560) | Municipality wide | * | * | * | * | 2,000.00 |  |  | 5,000.00 |  |  |  | Dep’t SWCD | Central Adm. |
| 132 | Social Services Delivery | social welfare &comm. dev | Support LEAP and Vulnerable to register with NHIA | Municipality wide | * | * | * | * | 7,481.40 |  |  | 5,000.00 |  |  |  | Dep’t SWCD | Central Adm. |
| 133 | Social Services Delivery | social welfare &comm. dev | Registration and Issuance of ID Cards to PWDs | Municipality wide | * | * | * | * |  |  |  | 000.00 |  |  |  | Dep’t SWCD | Central Adm. |
| 134 | Social Services Delivery | social welfare &comm. dev | Sensitize women and girls on teenage pregnancy | Municipality wide | * | * | * | * | 1,000 |  |  | 1,000 |  |  |  | Community Dev. | Central Adm. |
| 135 | Social Services Delivery | social welfare &comm. dev | Train School Feeding caterers on nutrition and food hygiene | Municipality wide | * | * | * | * |  |  |  | 1,000 |  |  |  | MHD | Central Adm. |
| 136 | Social Services Delivery | social welfare &comm. dev | Juvenile case handling / management | Municipality wide | * | * | * | * | 1,000.00 |  |  | 3,000.00 |  |  |  | Dep’t SWCD | Central Adm. |
| 137 | Social Services Delivery | social welfare &comm. dev | Sensitize communities and civil society organizations on the right of the child/ organize women groups to undertake income generating activities. | Municipality wide | * | * | * | * | 7,000.00 |  |  | 5,000.00 |  |  |  | Dep’t SWCD | Central Adm. |
| 138 | Social services delivery | social welfare &comm. dev | Sensitize child clubs in schools on child rights and protection | Municipality wide | * | * | * | * | 2,000.00 |  |  |  |  |  |  | Dep’t SWCD | Central Adm. |
| 139 | Environmental Sanitation and Management | Disaster prevention and management | Sanitation Improvement Package (SIP) | Municipality wide | * | * | * | * |  | 523,250.00 |  |  |  |  |  | MEHO | Central Adm. |
| 140 | Environmental Sanitation and Management | Disaster prevention and management | Procure 10No. Refuse Containers | Suhum | * | * | * | * |  | 220,000 |  |  |  |  |  | MEHU | Central Administration |
| 141 | Environmental Sanitation and Management | Disaster prevention and management | Undertake district Fumigation exercise day | Municipality wide | * | * | * | * |  | 418,600 |  |  |  |  |  | MEHU | Central Administration |
| 142 | Environmental Sanitation and Management | Disaster prevention and management | Regular dislodging of institutional and public toilets | Municipality wide |  |  |  |  |  | 386,957.08 |  |  |  |  |  | MEHU | Central Administration |
| 143 | Environmental Sanitation and Management | Disaster prevention and management | Desilting and dredging of public drains | Municipality wide | * | * | * | * |  | 100,000.00 |  |  |  |  |  | MEHO | Central Adm. |
| 144 | Environmental Sanitation and Management | Disaster prevention and management | Sanitation improvement package and fumigation and NALAG dues | Municipality wide | * | * | * | * |  | 70,000.00 |  |  |  |  |  | MEHO | SuMA |
| 145 | Environmental Sanitation and Management | Disaster prevention and management | Evacuation and Maintenance of Final Waste Disposal Site | Kwahyia | * | * | * | * |  | 200,000.00 |  |  |  |  |  | MEHO | Central Administration/MWD |
| 146 | Environmental Sanitation and Management | Disaster prevention and management | Organize National Sanitation Day | Municipality wide | * | * | * | * |  | 200,000 |  |  |  |  |  | MEHO | Central Adm. |
| 147 | Environmental Sanitation and Management | Disaster prevention and management | Monitoring and supervision of environmental service providers | Municipality wide | * | * | * | * |  | 10,000 |  |  |  |  |  | MEHO | Central Adm. |
| 148 | Environmental Sanitation and Management | Disaster prevention and management | Conduct sensitization on WASH activities | Municipality wide | * | * | * | * |  | 10,000 |  |  |  |  |  | MEHO | Central Adm. |
| 149 | Environmental Sanitation and Management | Disaster prevention and management | Provision of relieve items/ organize public education on climate change/bushfires and flood and World Disaster Day celebration in the municipality. | Municipality wide | * | * | * | * |  | 60,000.00 |  | 20,000.00 |  |  |  | NADMO | SuMA |
| 150 | Environmental Sanitation and Management | Disaster prevention and management | Provide for CC-DRR activities | Municipality wide | * | * | * | * |  | 20,000.00 |  | 10,000.00 |  |  |  | NADMO | SuMA |
| 151 | Environmental Sanitation and Management | Disaster prevention and management | support disaster mitigation measures | Municipality wide | * | * | * | * |  | 40,000.00 |  |  |  |  |  | NADMO | SuMA |
| 152 | Environmental Sanitation and Management | Disaster prevention and management | Organize Tree Planting Exercise and seedlings along rivers. | Municipality wide | * | * | * | * |  | 20,000 |  |  |  | * |  | NADMO | PPD SuMA |
| 153 | Infrastructure delivery and Management | Infrastructure Development | Installation, marking and maintenance of road furniture along selected roads | Suhum | * | * | * | * |  |  |  |  |  |  |  | UR | Central Adm. |
| 154 | Economic Development | Trade, Tourism Industrial Dev. | Provide business coaching services to entrepreneurs (WIDU) | Municipality wide | * | * | ,* | * |  |  |  | 2,000.00 |  |  |  | GEA | SuMA |
| 155 | Economic Development | Trade, Tourism Industrial Dev. | Carry out Business Counselling | Municipality wide | * | * | * | * |  |  |  | 2,000.00 |  |  |  | GEA | SuMA |
| 156 | Economic Development | Trade, Tourism Industrial Dev. | Organize financial literacy training for Dressmakers and Beauticians | Municipality wide | * | * | * | * |  |  |  | 2,000.00 |  |  |  | GEA | SuMA |
| 157 | Economic development | Trade, Tourism and Industrial Dev | Assistance in formalization of business in the informal sector to take advantage of government support packages | Municipality wide |  |  |  |  |  |  |  | 5,000.00 |  |  |  | GEA | SuMA |
| 158 | Economic Development | Health Delivery | Assembly’s contribution to local economic development (vocational training for the youth) | Suhum | * | * | * | * |  | 100,000.00 |  | 100,000.00 |  |  |  | GEA | Central Adm. |
| 159 | Economic Development | Trade, Tourism Industrial Dev. | Undertake Kaisen activities | Municipality wide | * | * | * | * |  |  |  | 2,000.00 |  |  |  | GEA | SuMA |
| 160 | Economic Development | Trade, Tourism Industrial Dev. | Support SMEs in agro-processing (Gari, Palm Oil and Vegetable production | Municipality wide | * | * | * | * |  |  |  | 30,000.00 |  |  |  | GEA | SuMA |
| 161 | Economic Development | Trade, Tourism Industrial Dev. | Conduct training session for 15 women in alternative livelihood | Municipality wide | * | * | * | * |  |  |  | 30,000.00 |  |  |  | GEA | SuMA |
| 162 | Economic Development | Trade, Tourism Indus. | Promote aquaculture development | Municipality wide | * | * | * | * |  |  |  | 30,000.00 |  |  |  | GEA | SuMA |
| 163 | Economic Development | Trade, Tourism Industrial Dev. | Assist SMEs to register their businesses | Municipality wide | * | * | * | * |  |  |  | 15,000.00 |  |  |  | GEA | SuMA |
| 164 | Economic Development | Trade, Tourism Industrial Dev. | Complete Construction of Industrial Workshop | Suhum | * | * | * | * |  | 20,231.80 |  |  |  |  |  | GEA | MWD |