SUHUM MUNICIPAL ASSEMBLY

Office of the Municipal Administration

P. O. Box 186

Tel: 0858-22363

Suhum.

23rd November, 2025

Office of the Municipal Administration

P. O. Box 186

Tel: 0858-22363

Suhum.

23rd November, 2025

In case of reply, the

Number and date of this

Letter should be quoted.

Our Ref--------------------

Your Ref-------------------

In case of reply, the

Number and date of this

Letter should be quoted.

Our Ref--------------------

Your Ref-------------------

`

SUBMISSION OF 2026 COMPOSITE ANNUAL ACTION PLAN.

I submit herewith the 2026 Annual Action Plan of the Suhum Municipal for your perusal and necessary action, please.

Thank You.

…………………………………………….....................

ALHAJI ABDUL-RAHIM TAHIDU MUSAH, ESQ

(MUNICIPAL COORDINATING DIRECTOR)

for: MUNICIPAL CHIEF EXECUTIVE

DISTRIBUTION

ALL HON. ASSEMBLY MEMBERS

SUHUM MUNICIPAL ASSEMBLY

ALL HEADS OF DEPARTMENTS/MPCU MEMBERS

SUHUM MUNICIPAL ASSEMBLY

Cc:

THE DIRECTOR

NATIONAL DEVELOPMENT PLANNING COMMISSION

ACCRA

ATTN.

REGIONAL ECONOMIC PLANNING OFFICER

SUHUM MUNICIPAL ASSEMBLY

DRAFT 2026 ANNUAL ACTION PLAN

OCTOBER, 2025

TABLE OF CONTENTS

Content……………………………………………………………………………………….Page

LIST OF ABBREVIATIONS	iii

CHAPTER ONE	1

MUNICIPAL PROFILE	1

1.1 Introduction	1

1.2. Vision and Mission	3

1.3. District Development Goal	3

1.4 Annual Action Plan (2026)	4

# LIST OF ABBREVIATIONS

AIDS                     Acquired Immunodeficiency Syndrome

DACF                    District Assemblies Common Fund

DACF – RFG         District Assemblies Common Fund Responsive Factor Grant

DDF                       District Development Fund

GoG                        Government of Ghana

HIV                         Human Immunodeficiency Virus

IGF                          Internally Generated Fund

MHD                       Municipal Health Directorate

MP’sCF                   Member of Parliament’s Common Fund

MPCU                      Municipal Planning Coordinating Unit

MTDP                      Medium Term- Development Plan

PWDsCF                   Person Living with Disability Fund

SuMA                        Suhum Municipal Assembly

CCE                            Community Conversation Enhancement

RCC                          Regional Coordinating Council

REPO                        Regional Economic Planning Officer

NDPC                       National Development Planning Commission

# MUNICIPAL PROFILE

## 1.1 Introduction

The 2026 Annual Action Plan is an extraction from the District Medium Term Development Plan (DMTDP-2026-2029).  It outlines prioritized programmes and activities that are intended to be implemented in 2026.  These programmes and their objectives constitute the road map in the municipality’s efforts to meet the District Medium Term Development Goal. The priority interventions for 2026 seek to address five main issues hindering the growth of   the municipality.  These include weak human resource base, low agricultural productivity, weak institutional capacity for service delivery, weak revenue mobilization and management capacity and poor infrastructure development. This plan is therefore the strategy to deal holistically with these problems and to provide a sustainable foundation for the accelerated development of the Municipality within the context of the National Development Strategy.

#### 1.1.1	Administration

The Suhum Municipality is one of the 33 administrative districts in the Eastern Region of Ghana. It used to be part of the defunct Suhum-Kraboa-Coaltar District until the Ayensuano District was carved out of it in July 2012 and Suhum elevated to a municipality status.

#### 1.1.2	LI Establishing the Municipality

It was established in July 2012 by Legislative Instrument (L.I.) 2048 and Suhum is the municipal capital.

#### 1.1.3	Population

The municipality has a population of 126,403 made up of 61,226 (48.7%) males and 65,177 (51.3%) females. This represents about three percent (3.4%) of the total population of the Eastern Region.  Also, 37.8 percent of the population are within the age group 0-14years (children), while 32.3 percent are youth (15-34 years) with 5.9 percent being aged (65+ years). According to MPCU projection based on 2010 population census.

#### 1.1.4	Municipal Economy

The economy of the municipality comprises agriculture, service, commerce and light industrial sectors. However, the details of these sectors are elaborated in the sections below.

##### 1.1.4.1	Agricultural Activities3

More than half (57.8%) of households in the Municipality are engaged in agriculture. In terms of rural-urban distribution, the number of households engaged in agriculture in the rural areas (74.7%) is almost three times the number in the urban areas (25.3%). Most of the agricultural activities in the Municipality therefore take place in the rural areas.

Crop farming in the Municipality is very dominant in the rural areas. The number of households engaged in crop farming in the rural areas (77.4%) is about three times more than the number in urban areas (22.6%). Tree planting and livestock rearing is practiced by over 80 percent (80.6 and 81.2 percent respectively) of rural agricultural households which is four times higher than the number of agricultural households in the urban areas who are engaged in tree planting (19.4%) and livestock rearing (18.8%).

##### 1.1.4.2	Literacy and Education

In the Suhum Municipality, 85.1 percent of the population aged 11 years and older are literate. In all 19.5 percent of the population in the Municipality can read and write English only while 88.0 percent can read and write English and another language. The proportion of literate males to females is 91.6 percent and 79.5 percent respectively. However, the proportion of illiterate females (20.5%) is more than twice that of males (8.8%).

Six out of every ten (61.8%) persons who have attended school in the past have JSS/JHS or middle school as the highest level attained. The proportion of male tertiary graduates (5.0%) is more than twice the proportion of corresponding females (2.1%).

##### 1.1.4.3	Other Economic Characteristics- Sector and Activity

Generally, seven in ten (74.8%) persons aged 15 years and older in the Municipality are economically active. Among the economically active population, nine in ten persons (95.0%) are employed while 5.0 percent are not employed. There is not much gap between the proportion of males and females as 75.9 percent and 73.9 percent respectively are economically active.

Economic activity is lowest among the age group 15-19 years with 23 percent being economically active while 77 percent are not economically active. Among the economically active within that age group, 87.6% are employed with the rest (12.4%) not employed. Economic activity starts rising from the age group 20-24 years (70.3%) and peaks at 95.8 percent at 45-49 years and begins to fall consistently from the ages 50-54 (93.8%).

Agriculture, including forestry and fishing (37.7%) constitute the major industry of the employed population in the Suhum Municipality. Other major industries are wholesale and retail; repair of motor vehicles and motorcycles (21.9%), manufacturing (11.5%) and accommodation and food service activities (5.9%).

## 1.2. Vision and Mission

#### 1.2.1 Vision Statement

An environmentally friendly and economically viable Municipality with adequate and accessible amenities for the people to actualise their dreams and enjoy peaceful co-existence.

#### 1.2.2	Mission Statement

The Suhum Municipal assembly exists to constantly upgrade the quality of life of the people in the Municipality through the efficient mobilization and utilization of resources within an effective participatory local governance framework.

## 1.3. District Development Goal

The basic goal of the District Medium Term Plan (2026-2029) is to address the high levels of poverty in the district by creating the enabling environment for increased production and productivity and improvement in the delivery of basic services.

## 1.4 Annual Action Plan (2026)

For the Suhum municipal Assembly to achieve its objectives and realize its broad goal, with the aim to promoting the general well-being of the people, there are a number of programmes and projects to be undertake from January to December 2026. The table 1 below shows the various activities.

Table 1: Annual Action Plan, 2026

| Programme (PBB) | Sub-Programme (PBB) | Broad Activities | Location | Time frame Quarterly |  |  |  | Cost |  |  |  |  | Programme status |  | Implementing Institutions/Departments |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | DACF | DACF-RFG | IGF | DONOR | New | On-going | Lead | Collab. |
| Management and Admin | Finance | Purchase of utility (water, electricity and data) | Suhum | * | * | * | * |  |  |  | 50,000.00 |  |  |  | Finance | Central Administration |
| Management and Admin | Finance | Provide for allowances, T&T, and grants | Suhum | * | * | * | * |  |  |  | 100,000.00 |  |  |  | Finance | Central Administration |
| Management and Admin | Finance | Purchase value books | Accra | * | * | * | * |  |  |  | 20,000.00 |  |  |  | Finance | Central Administration |
| Management and Admin | Finance | Provide for compensation, commission and casual laborers | Suhum | * | * | * | * |  |  |  | 350,000.00 |  |  |  | Finance | Central Administration |
| Management and Administration | General Administration | Donations /contributions to National programmes, official celebrations and scholarships | Suhum |  |  |  |  |  | 90,000.00 |  | 250,000.00 |  |  |  | Finance | Central Administration |
| Management and Admin | General Administration | Procure stationery, Consumables and swivel chairs for Assembly | Suhum | * | * | * | * |  | 46,011.36 |  | 40,000.00 |  |  |  | Procurement | Central Adm. |
| Management and Admin | Finance | Data Collection (Revenue Data Update) | Suhum | * | * | * | * |  | 15,000.00 |  |  |  |  |  | Finance | Central Adm. |
| Management and Admin | General Administration | Provide for Hotel Accommodation for official guests | Suhum | * | * | * | * |  |  |  | 10,000.00 |  |  |  | Finance | Central Administration |
| Management and Admin | General Administration | Maintenance & Repairs of official vehicles | Suhum | * | * | * | * |  | 60,000.00 |  | 50,000.00 |  |  |  | Transport | Central Administration |
| Management and Admin | General Administration | Training programme for Assembly Drivers | Suhum | * | * | * | * |  |  |  | 6,000.00 |  |  |  | Transport | Central Administration |
| Management and Admin | Finance | Purchase of fuel and lubricants for official vehicles and motorbikes | Suhum | * | * | * | * |  | 91,500.00 |  | 170,000.00 |  |  |  | Transport | Central Administration |
| Management and Admin | General Administration | Maintenance /Rehabilitation/Repairs of office building | Suhum | * | * | * | * |  | 180,000.00 |  | 20,000.00 |  |  |  | MWD | Central Administration |
| Management and Admin | Finance | Provision of insurance, Running Expenses of official vehicles | Suhum | * | * | * | * |  | 94,000.00 |  | 15,000.00 |  |  |  | Finance | Central Administration |
| Management and Admin | General Administration | Maintenance of furniture & fixtures | Suhum | * | * | * | * |  | 70,000.00 |  | 10,000.00 |  |  |  | Finance | Central Administration |
| Management and Admin | General Administration | Payment for various meeting (Tender Com, MPCU Sub.com, GA, ETC) | Suhum | * | * | * | * |  |  |  | 269,009.83 |  |  |  | Finance | SuMA |
| Management and Admin | Finance | Bank charges and payment of tax liability. | Suhum | * | * | * | * |  | 4,000.00 |  | 600.00 |  |  |  | Finance | SuMA |
| Management and Admin | Finance | Revenue improvement monitoring, education and sensitization of rate payers (RIAP) | Municipality wide | * | * | * | * |  |  |  | 40,000.00 |  |  |  | Finance | SuMA |
| Management and Admin | General Administration | Quarterly project monitoring | Municipality wide | * | * | * | * |  | 40,000.00 |  | 10,000.00 |  |  |  | MPCU | SuMA |
| Management and Admin | General Administration | Gazzeting/Publication of official documents (By-Laws) of the Assembly | Suhum | * | * | * | * |  | 65,000.00 |  | 30,000.00 |  |  |  | Finance | SuMA |
| Management and Admin | General Administration | Public sensitization/Town hall meetings /meet the press | Municipality wide | * | * | * | * |  | 60,000.00 |  | 50,000.00 |  |  |  | MPCU | SuMA |
| Management and Admin | General Administration | Established Post | Suhum |  |  |  |  | 3,985,227.01 |  |  |  |  |  |  |  | Central Adm. |
| Management and Admin | General Administration | Purchase of office equipment and Logistics : steel cabinets, laptops etc. | Suhum | * | * | * | * |  | 90,000.00 |  | 20,000.00 |  |  |  | MPCU | SuMA |
| Management and Admin | General Administration | Purchase of office Furniture | Suhum | * | * | * | * |  | 100,000.00 |  |  |  |  |  | MPCU | SuMA |
| Management and Admin | General Administration | Provide Logistical Support to Decentralized Department | Suhum | * | * | * | * |  | 30,000.00 |  |  |  |  |  | Central Administration | SuMA |
| Management and Admin | General Administration | Furnishing of the 3 Zonal councils: curtains, furniture, printers, photocopiers, desktop computers, UPS, | Suhum | * | * | * | * |  | 50,0000.00 |  | 5,000.00 |  |  |  | MPCU | SuMA |
| Management and Admin | General Administration | Support the Operationalization and Functionality of Sub-structures | Suhum | * | * | * | * |  | 20,000.00 |  | 5,000.00 |  |  |  | MPCU | SuMA |
| Management and Admin | Planning, Budgeting and Co-ordination | Review 2026 budget and prepare 2027 composite budget and fee fixing document. | Suhum | * | * | * | * |  | 65,000.00 |  | 20,000.00 |  |  |  | MPCU | SuMA |
| Management and Admin | Planning, Budgeting and Co-ordination | Review of 2026 Annual Action Plan Prepare 2027 AAP | Suhum | * | * | * | * |  | 50,000.00 |  |  |  |  |  | MPCU | SuMA |
| Management and Admin | Planning, Budgeting and Co-ordination | Gazzeting of Fee Fixing Resolution | Suhum | * | * | * | * |  | 65,500.00 |  |  |  | * |  | MPCU | SuMA |
| Management and Admin | General Administration | MP’s general contribution to community development | Municipality wide | * | * | * | * |  | 303,155.36 |  |  |  |  |  | MP | SuMA |
| Management and administration | Human resource management | Preparation of capacity building plans. | Suhum | * | * | * | * | 5,000.00 |  |  | 5,000.00 |  |  |  | HR | SuMA |
| Management and administration | Human resource management | Revenue Mobilization Strategies | Suhum | * | * | * | * |  |  |  | 3,000.00 |  |  |  | HR | SuMA |
| Management and administration | Human resource management | Enterprise Risk Management/ Performance Audit/ IT Audit | Suhum | * | * | * | * |  |  |  | 2,000.00 |  |  |  | HR | SuMA |
| Management and administration | Human resource management | PMS Appraisal | Suhum | * | * | * | * |  |  |  | 2,000.00 |  |  |  | HR | SuMA |
| Management and administration | Human resource management | Training Needs Assessment | Suhum | * | * | * | * |  |  |  |  |  |  |  | HR | SuMA |
| Management and administration | Human resource management | Minutes & Report Writing | Suhum | * | * | * | * |  |  |  | 2,000.00 |  |  |  | HR | SuMA |
| Management and administration | Human resource management e | Preparation and submission of personnel updates and inputs | Suhum | * | * | * | * | 3,000.00 |  |  | 5,000.00 |  |  |  | HR | SuMA |
| Management and administration | Information Management | Maintenance of Municipal assembly Website | Suhum | * | * | * | * |  | 5,000.00 |  | 5,000.00 |  | * |  | MIS Unit | SuMA |
| Management and administration | Information Management | Installment of Internet Infrastructure and Internet Data | Suhum | * | * | * | * |  |  |  | 45,000.00 |  |  | * | MIS Unit | SuMA |
| Management and administration | Information Management | Procurement of 2No. 1 Terabyte External Hard drive for Storage of Assembly Data/ Document | Suhum | * | * | * | * |  |  |  | 1,600.00 |  | * |  | MIS Unit | Procurement Unit |
| Management and administration | Information Management | Repairs and Maintenance of Various Office Equipment | Suhum | * | * | * | * | 15,000.00 |  |  | 10,000.00 |  |  | * | MIS Unit | Central Administration |
| Management and administration | Information Management | Procurement of Extension Boards For MIS Units | Suhum | * | * | * | * | 1,000.00 |  |  | 1,000.00 |  | * |  | Central Administration | MIS Unit |
| Management and administration | Information Management | Procurement of Scanners | Suhum | * | * | * | * | 7,000.00 |  |  |  |  | * |  | MIS Unit | Central Administration |
| Management and administration | Information Management | Procurement Of Photocopier Machine | Suhum | * | * | * | * | 22,000.00 |  |  |  |  | * |  | Central Administration | MIS Unit |
| Management and administration | Information Management | Procurement of Giant Staple Machine | Suhum | * | * | * | * |  |  |  | 1,000.00 |  | * |  | Central Administration | MIS Unit |
| Management and administration | Information Management | Procurement 10No. Anti-Virus (3 in 1) | Suhum | * | * | * | * | 5,500.00 |  |  |  |  |  | * | MIS Unit | Central Administration |
| Management and administration | Information Management | Procurement of Window Activation | Suhum | * | * | * | * |  |  |  | 4,000.00 |  |  |  | MIS Unit | Central Administration |
| Management and administration | Information Management | Procurement of UPS | Suhum | * | * | * | * |  |  |  | 10,000.00 |  | * |  | MIS Unit | Central Administration |
| Management and administration | Human resource management | Organize Manpower Development Workshop and Capacity building. | Suhum | * | * | * | * |  | 30,000.00 |  |  |  | * |  | HR |  |
| Management and administration | Security Management | Support Security Operations | Suhum | * | * | * | * |  | 100,000.00 |  |  |  | * |  | MuSEC | SuMA |
| Management and Admin | General Administration | NALAG Dues and Subscription | Suhum | * | * | * | * |  | 70,201.83 |  |  |  | * |  | Finance | SuMA |
| Infrastructure Delivery and Management | General Administration | Completion of Renovation, Furnishing and Upgrade of PA System of Conference Room Block at Ministries – Suhum | Suhum | * | * | * | * |  | 211,348.00 |  |  |  |  |  | MWD | SuMA |
| Infrastructure Delivery and Management | General Administration | Completion of Rehabilitation works on Official Bungalows at suhum | Suhum | * | * | * | * |  | 1,200,000.00 |  |  |  |  |  | MWD | SuMA |
| Infrastructure Delivery and Management | General Administration | Completion of ICT Installation, Furnishing, and Rehabilitation of Assembly’s Main Block – Suhum | Suhum | * | * | * | * |  | 216,740.00 |  |  |  |  |  | MWD | SuMA |
| Economic Development | Agriculture Development | Maintenance of official vehicle. | Suhum | * | * | * | * | 6,000.00 |  |  |  | 6,000.00 | * |  | Agric Dep:t | SuMA |
| Economic Development | Agriculture Development | Maintenance of 19 official motorbikes. | Agric Dept | * | * | * | * | 4,000.00 |  |  |  | 6,000.00 | * |  | Agric Dep:t | SuMA |
| Economic Development | Agriculture Development | Arrange for the maintenance of office computers, accessories and other equipment | Agric Dept | * | * | * | * | 2,000.00 |  |  |  | 2,000.00 | * |  | Agric Dep:t | SuMA |
| Economic Development | Agriculture development | Provision of Insurance on all official motorbikes and vehicles | Suhum | * | * | * | * | 4,000.00 |  |  |  | 8,000.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture development | Procure tyres for official vehicle | Agric Dept |  | * |  |  | 2,000.00 |  |  |  | 3,000.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture development | Pay for Utility Bill, Call Credit and Data Bundle | Suhum | * | * | * | * | 2,000.00 |  |  |  | 4,000.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture development | Procure stationeries | Agric Dept | * | * | * | * | 2,000.00 |  |  |  | 3,000.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture development | Procure equipment to conduct crop yield study | Agric Dept | * | * | * | * | 4,000.00 |  |  |  | 4,000.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Monitoring, supervision and publicity on planned flagship projects. | Municipality wide | * | * | * | * | 4,000.00 |  |  |  | 8,000.00 |  |  | Agric Dep:t | SuMA |
| Economic Development | Agriculture Development | Servicing of RELC, review meetings, public forum, field day sessions and other extension services meeting | Municipality wide | * | * | * | * |  |  |  | 2,000.00 | 15,000.00 |  |  | Agric Dep:t | SuMA |
| Economic Development | Agriculture Development | Organize Field day for 30women and 20 men farmers | Municipality wide | * | * | * | * | 2,500.00 |  |  |  | 2,500.00 |  |  | Agric Dep:t | SuMA |
| Economic Development | Agriculture Development | Conduct Research Extension Farmer Linkage Committee (RELC) meeting | Municipality wide | * | * | * | * | 6,000.00 |  |  |  | 6,000.00 | * |  | Agric Dep:t | SuMA |
| Economic Development | Agriculture Development | Procure protective clothing and PPE | Municipality wide | * | * | * | * | 4,000.00 |  |  |  | 2,000.00 |  |  | Agric Dep:t | SuMA |
| Economic Development | Agriculture Development | Training 40 staff on various improved technology | Municipality wide | * | * | * | * | 6,000.00 |  |  |  | 6,000.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Enhance skills and knowledge of staff on system of Rice Intensification (SRI) Technologies | Municipality wide | * | * | * | * | 2,000.00 |  |  |  | 2,500.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Facilitate staff performance through workshops, Technical review meeting and capacity building | Municipality wide | * | * | * | * | 3,000.00 |  |  |  | 3,000.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Train staff on Technical Education for Modernizing Agriculture in Ghana (TEDMAG) | Municipality wide | * | * | * | * | 2,500.00 |  |  |  |  | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Enhance the skills and knowledge level of livestock women farmers on endo and ecto – parasite control | Municipality wide | * | * | * | * | 2,500.00 |  |  |  |  | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Training of staff on emergency preparedness on emerging livestock diseases | Municipality wide | * | * | * | * |  |  |  |  | 3,000.00 |  |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Train 15 women farmers on climate smart agriculture | Suhum Municipality | * | * | * | * |  |  |  |  | 1,000.00 |  |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Tran 50 farmers in non- traditional agriculture | Suhum Municipality | * | * | * | * | 2,500.00 |  |  |  |  | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Promote vegetable production through irrigation | Suhum Municipality | * | * | * | * | 2,500.00 |  |  |  | 2,500.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Promote climate smart agriculture among farmers | Suhum Municipality | * | * | * | * | 2,500.00 |  |  |  | 2,500.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Train 20 palm fruit processing women in value addition | Suhum Municipality | * | * | * | * | 2,000.00 |  |  |  | 4,000.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Conduct training session for 25 women in additional livelihood | Municipality wide | * | * | * | * | 2,500.00 |  |  |  | 2,000.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Conduct training for 15 Women extension volunteers and animators on crop disease and pets identification and control | Municipality wide | * | * | * | * | 2,500.00 |  |  |  | 2,500.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Identify and resource female farmers living with disability in income generation activities | Municipality wide | * | * | * | * | 3,000.00 |  |  |  | 3,000.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Provide 20 women farmers improved crop varieties and taroo planting materials | Municipality wide | * | * | * | * | 4,000.00 |  |  |  |  |  |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Train 20 women in post-harvest management of fresh vegetables | Municipality wide | * | * | * | * |  |  |  |  | 2,000.00 |  |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Train 40 farmers on post – harvest management of cereals | Suhum Municipality | * | * | * | * | 3,000.00 |  | 3,00.00 |  | 3,000.00 | * |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Promote the establishment of backyard vegetables garden for women | Municipality wide | * | * | * | * | 2,500.00 |  |  |  | 2,500.00 |  |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Conduct demonstration on cereal, vegetable | Municipality wide | * | * | * | * | 2,500.00 | 2,500.00 | 2,500.00 | 2,500.00 | 2,500.00 | * |  | Agric Dept. | SuMA |
| Economic development | Agriculture Development | Undertake Municipal Planning Coordination Unit Track the implementation of planned activities | Municipality wide | * | * | * | * | 4,000.00 | 4,000.00 | 4,000.00 |  | 4,000.00 |  |  | Agric Dept. | SuMA |
| Economic development | Agriculture Development | Support implementation of Agriculture activities | Municipality wide | * | * | * | * |  | 30,000.00 |  |  |  |  |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Organize technical review meetings | Suhum municipality | * | * | * | * |  |  |  |  | 1,500.00 |  |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Train 15 women farmers in aflatoxin prevention and control in cereals and legumes | Suhum municipality | * | * | * | * |  |  |  |  | 1,500.00 |  |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Vaccinate animals against rabies and schedule diseases | Municipality wide | * | * | * | * |  |  |  | 3,000.00 |  |  |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Train technical staff to improve upon technical skills and knowledge (TECMAG). |  | * | * | * | * |  |  |  |  | 2,000.00 |  |  | Agric Dept. | SuMA |
| Economic Development | Agriculture development | MDA monitor implementation of Agricultural activities |  |  |  |  |  | 1,000.00 |  |  |  | 5,450.00 |  |  | Agric Dept. | SuMA |
| Economic Development | Agriculture development | Facilitate staff participation in training and workshops | Suhum Municipal | * | * | * | * |  |  |  |  | 2,200.00 |  |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Strengthen women groups towards the development of commodity satellite market activities | Municipality wide | * | * | * | * | 2,500.00 |  |  |  | 3,000.00 |  |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Celebration of 41st farmer’s day. | Municipality wide | * | * | * | * |  | 80,000.00 |  | 20,000.00 |  |  |  | Agric Dep:t | SuMA |
| Economic Development | Agriculture Development | WIAD and LED activities | Municipality wide | * | * | * | * |  |  |  |  | 6,000.00 |  |  | Agric Dep:t | SuMA |
| Economic Development | Agriculture Development | Train 20 rearing for Food and Jobs Farmers on treatment against livestock disease | Sushum municipality | * | * | * | * | 1,000.00 |  |  |  | 1,000.00 |  |  | Agric Dep.t | SuMA |
| Economic Development | Agriculture Development | Conduct crop and livestock disease surveillance to enhance the rearing for Food and Jobs Campaign | Sushum municipality | * | * | * | * | 2,000.00 |  | 2,000.00 |  | 2,000.00 | * |  | Agric Dep.t | SuMA |
| Economic Development | Agriculture Developmeng | Conduct market survey to determine prices of agricultural produce | Municipality wide | * | * | * | * | 2,000.00 |  |  |  | 2,000.00 | * |  | Agric Dep.t | SuMA |
| Economic Development | Agricultre Development | Conduct field demonstration and agricultural yield study. | Municipality wide | * | * | * | * | 4,000.00 |  |  |  | 6,000.00 |  |  | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Provide extension services to 2100 farmers through the conduct of home and farm visits. | Municipality wide | * | * | * | * | 30,000.00 | 20,000.00 | 20,000.00 | 20,000.00 | 60,000.00 |  | * | Agric Dept. | SuMA |
| Economic Development | Agriculture Development | Support to various flagship projects and contributions to national programmes. | Suhum | * | * | * | * |  | 26,000.00 |  |  | 20,000.00 |  |  | Agric Dep:t | SuMA |
| Economic Development | Agriculture Development | Support SMEs in agro-processing (Gari, Palm Oil and Vegetable production | Suhum |  |  |  |  |  |  |  |  |  |  |  | Agric Dep:t | SuMA |
| Economic Development | Agriculture Development | Procure Start – Up Kits to support PWDS businesses | Suhum |  |  |  |  |  |  |  |  |  |  |  | Agric Dep:t | SuMA |
| Economic Development | Statistics | Develop and update municipal data hub. | Suhum | * | * | * | * | 8,000.00 |  |  | 2,000.00 |  |  |  | SD | Central Adm. |
| Infrastructure Development | Physical Planning | Inspection of sites for processing development applications for Dev. Permit | Suhum | * | * | * | * | 3000 |  |  |  |  |  |  | PPD | SuMA |
| Infrastructure Development | Physical Planning | Holding of monthly Technical-Sub Planning Committee meetings. | Suhum | * | * | * | * | 3000 |  |  |  |  |  |  | PPD | SuMA |
| Infrastructure Development | Physical Planning | Holding of monthly Spatial Planning Committee meetings. | Suhum | * | * | * | * | 3000 |  |  |  |  |  |  | PPD | SuMA |
| Infrastructure Development | Physical Planning | Planning Education for three (3) selected Communities without Local Plans | Suhum | * | * | * | * | 3000 |  |  |  |  |  |  | PPD | SuMA |
| Infrastructure Development | Physical Planning | Preparation of site plans for at least five lands | Suhum | * | * | * | * | 3000 |  |  |  |  |  |  | PPD | SuMA |
| Infrastructure Development | Physical Planning | Properties own by SuMA (Continuation) | Suhum | * | * | * | * | 3000 |  |  |  |  |  |  | PPD | SuMA |
| Infrastructure Development | Physical Planning | Preparation & completion of Local Plan for Tei Mensah, Tete Nkwanta & Obretema | Suhum | * | * | * | * | 3000 |  |  |  |  |  |  | PPD | SuMA |
| Infrastructure Development | Physical Planning | Street Naming & Property Addressing-Data Collection & 10% increment of street named with signage | Suhum | * | * | * | * |  | 3000 |  |  |  |  |  | PPD | SuMA |
| Infrastructure Development | Physical Planning | Preparation of Spatial Development Framework (SDF) | Suhum | * | * | * | * |  | 3000 |  |  |  |  |  | PPD | SuMA |
| Infrastructure Development | Physical Planning | Preparation of Structure Plan (SP) | Suhum | * | * | * | * |  | 3000 |  |  |  |  |  | PPD | SuMA |
| Infrastructure Development | Physical Planning | Acquisition of Assets: office equipment. | Suhum | * | * | * | * |  | 3000 |  |  |  |  |  | PPD | SuMA |
| Infrastructure Development | Physical Planning | Established | Suhum | * | * | * | * | 125,843.66 |  |  |  |  |  |  | Physical planning | Central Admin |
| Infrastructure | Physical Planning | Street Naming and Data collection | Suhum | * | * | * | * | 4,000.00 |  |  | 5,000.00 |  |  |  | PP | Central Amin |
| Infrastructure Delivery and Management | Infrastructure Development | Grading of selected Roads (9.66KM) | Suhum and environs | * | * | * | * |  |  |  |  |  |  |  | UR | Central Adm. |
| Infrastructure Delivery and management | Infrastructure development | Procurement of office equipment/ organize public education on planning schemes | Suhum and environs | * | * | * | * | 4,000.00 |  |  | 5,000.00 |  |  |  | Works department | Central Admin |
| Infrastructure and delivery management | Infrastructure development | Drilling of 10 No. Boreholes | Selected communities |  |  |  |  |  |  |  |  |  |  |  | Works department | Central Admin |
| Infrastructure and service delivery | Infrastructure development | Established post |  | * | * | * | * | 411,507.00 |  |  |  |  |  |  | Works | Central Administration |
| Infrastructure and service delivery | Infrastructure development | IGF Capital Project(Pavement of Assembly Compound |  | * | * | * | * | 500,000.00 |  |  |  |  |  |  | Works | Central Administration |
| Infrastructure and service delivery | Infrastructure development | Construction of 4 bedroom MCE Bungalow at Suhum | Suhum | * | * | * | * |  | 1,200,000.00 |  |  |  |  |  | Works | Central Administration |
| Infrastructure and service delivery | Infrastructure development | MP’s Capital Projects | Suhum | * | * | * | * |  | 1,700,000.00 |  |  |  |  |  | Works | Central Administration |
| Infrastructure and service delivery | Infrastructure development | Land Acquisition and registration | Suhum | * | * | * | * |  | 840,000.00 |  |  |  |  |  | Works | Central Administration |
| Infrastructure Delivery and Management | Infrastructure Development | Desilting of streams and routine cleansing of open drains, kerbs and culverts in selected locations | Suhum | * | * | * | * |  | 81,000.00 |  |  |  |  |  | UR | Central Adm. |
| Economic development | Agriculture | Sensitization and vaccination of domestic animals/pets in the municipality. | Suhum | * | * | * | * |  |  |  | 10,000.00 |  |  |  | Agric Dept. | Central Adm. |
| Infrastructure Delivery and Management | Infrastructure Development | Conduct monitoring and inspections | Municipality wide | * | * | * | * | 5,000.00 |  |  | 2,000.00 |  |  |  | UR | Central Adm. |
| Infrastructure Delivery and Management | Infrastructure Development | Prepare Municipal Spatial Development Framework | Municipality wide | * | * | * | * |  | 20,000.00 |  |  |  |  |  | PPD | Central Administration |
| Infrastructure Delivery and Management | Infrastructure Development | Spatial Planning committee meetings and land use education | Municipality wide | * | * | * | * | 2,000.00 |  |  | 2,000.00 |  |  |  | PPD | Central Administration |
| Infrastructure Delivery and Management | Infrastructure Development | Inspection of site for permit/Conduct Public Education on National Building Regulations of 1996(L.I. 1630) | Municipality wide | * | * | * | * | 3,000.00 |  |  | 12,000.00 |  |  |  | PPD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Completion of 3 storey market complex (1st phase 16 unit Multi-Purpose Storey Lockable Stores ) at Suhum Amponsah market | Suhum Amponsah market | * | * | * | * |  | 800,000.00 |  |  |  |  |  | MWD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Completion of 3 storey market complex (2nd and 3rd phase 32 unit Multi-Purpose Storey Lockable Stores ) at Suhum Amponsah market | Suhum Amponsah market | * | * | * | * |  | 1,549,380.55 |  |  |  |  |  | MWD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Completion of 1No. police station with accommodation at Akorabo | Akorabo | * | * | * | * |  | 500,000.00 |  |  |  |  |  | MWD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Completion of Rehabilitation and Furnishment of Phi-beta ICT Center Suhum | Suhum | * | * | * | * |  | 150,122.00 |  |  |  |  |  | MWD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Construction and drilling of 10 No boreholes in selected communities |  | * | * | * | * |  |  | 200,000.00 |  |  |  |  | MWD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Support to community-initiated help projects | Municipality wide | * | * | * | * |  | 194,885.59 |  |  |  |  |  | MWD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Refurbishment of Municipal Chief Executive’s official residency |  | * | * | * | * |  | 60,000.00 |  | 40,000.00 |  |  |  | MWD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Completion of 1No. 4 seater KVIP at Suhum Methodist School | Suhum Methodist JHS | * | * | * | * |  | 100,122.00 |  |  |  |  |  | MWD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Routine inspection and supervision | Municipality wide | * | * | * | * |  |  |  | 5,000.00 |  |  |  | MWD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Purchase of printed material and stationery | Suhum | * | * | * | * |  |  |  | 5,000.00 |  |  |  | MWD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Purchase of petty tools | Suhum | * | * | * | * |  |  |  | 2,000.00 |  |  |  | MWD | Central Administration |
| Infrastructure Delivery and Management | Infrastructure Development | Completion of Toilet Facilities at Kwabena Kumi (20Seater) MBDA | Kwabena Kumi | * | * | * | * |  | 100,000.00 |  |  |  |  |  | MWD | Central Administration |
| Infrastructure Delivery and Management | Infrastructure Development | Completion of 1No. Toilet Facilities at Jato (10Seater) MBDA | JATO | * | * | * | * |  | 50,000.00 |  |  |  |  |  | MWD | Central Administration |
| Infrastructure Delivery and Management | Infrastructure Development | Completion of 1No. Toilet Facilities at AKOTE (10Seater) MBDA | AKOTE | * | * | * | * |  | 50,000.00 |  |  |  |  |  | MWD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Rehabilitate and reshape feeder roads | Municipality wide | * | * | * | * |  | 200,000.00 |  |  |  |  |  | MWD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Construct a duty post for staff at cemetery | Suhum | * | * | * | * |  |  |  | 50,000.00 |  |  |  | MWD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Rehabilitation of assembly store room | Suhum | * | * | * | * |  |  |  | 10,000.00 |  |  |  | MWD | Central Administration |
| Infrastructure and delivery management | Infrastructure Development | Support to the departmental activities and functioning. | Suhum | * | * | * | * | 15,000.00 |  |  |  |  |  |  | MWD | Central Administration |
| Infrastructure Delivery and Management | Infrastructure Development | Rehabilitation of streetlight and street naming and data collection. | Municipality wide | * | * | * | * | 4,00000 | 80,000.00 |  | 35,000.00 |  |  |  | SuMA | ECG |
| Infrastructure Delivery and Management | Infrastructure Development | Extension of electricity | Municipality wide | * | * | * | * |  | 200,000.00 |  |  |  |  |  | SuMA | ECG |
| Infrastructure and delivery management | Infrastructure Development | Construction of 1 No. Storey building Health Center. | Ayekotse | * | * | * | * |  |  | 2.250,000 |  |  |  |  | GHS | SuMA |
| Infrastructure and delivery management | Infrastructure Development | Construction of 32 lockable Stores. | Suhum | * | * | * | * |  |  | 3,040,323.16 |  |  |  |  | MWD | SuMA |
| Infrastructure and delivery management | Infrastructure Development | Construction of Artisanal Village. | Suhum | * | * | * | * |  |  | 2,000,000.00 |  |  |  |  | MWD | SuMA |
| Infrastructure and delivery management | Infrastructure Development | Pavement of the Suhum Urban Council and Construction of 4-Seater Toilet and Urinal | Suhum Urban Council | * | * | * | * |  |  | 633,191.84 |  |  |  |  | MWD | SuMA |
| Capacity building | Human Resources | Capacity Building. | Municipality Wide | * | * | * | * |  |  | 289,864.00 |  |  |  |  | HR | SUMA |
| Infrastructure and delivery management | Infrastructure Development | Completion of Reshaping of roads and Gravelling of selected Roads Municipal Wide (20KM) | Municipal Wide | * | * | * | * |  | 35,328.00 |  |  |  |  |  | MWD | Central Administration |
| Infrastructure Delivery and Management | Infrastructure Development | Complete Drilling and Mechanization of 1No. Borehole/Fire Hydrant with 10ft square double slab, 28ft high overhead Tank with 50mm diameter Galvanized pipe with ladder fixed in the column, Drilling of 80-100m Well, installation of specified /approved 3.0.HP pump with accessories, supply and installation of water Tank. (2No. 5000Liters), supply and installation of switch board and connect to ECG grid at suhum fire service complex. | Suhum | * | * | * | * |  | 160,000.00 |  |  |  | * |  | MWD | Central Administration |
| Social Services Delivery | Infrastructure Development | Complete Drilling and Mechanization of 5No. Institutional Borehole with 8ft square single slab, 12ft high overhead Tank, Drilling of 60-100m Well, installation of specified /approved 2.0.HP pump with accessories, supply and installation of water Tank. (4000 Liters), supply and installation of switch board with separate meter and connect to ECG Grid at Akorabo CHPS Compound, Abenabo CHPS compound, Adarkwa Primary School Akoabo 3Unit Classroom, Kokooso KG and Nursery | Selected community | * | * | * | * |  | 500,000.00 |  |  |  | * |  | MWD | Central Administration |
| Infrastructure Delivery and Management | Infrastructure Development | Complete Drilling and Mechanization of 1No. Borehole with 10ft square single slab, 28ft high overhead Tank with 50mm diameter Galvanized pipe ladder fixed in the column, Drilling of 80-100m Well, installation of specified /approved 2.5.HP pump with accessories, supply and installation of water Tank. (5000Liters), pipe works connection, supply and installation of switch board with separate meter and connect to ECG grid at suhum fire – Residency Enclave complex. | Suhum | * | * | * | * |  | 150,000.00 |  |  |  | * |  | MWD | Central Administration |
| Social Services Delivery | Infrastructure Development | Complete Drilling and Mechanization of 8No. Institutional Borehole with 8ft square single slab, 12ft high overhead Tank, Drilling of 60-100m Well, installation of specified /approved 2.0.HP pump with accessories, supply and installation of water Tank. (4000 Liters), supply and installation of switch board with separate meter and connect to ECG Grid at Odokum, Down Villa, Niifio, Ahafi, Dawn of Life, Kokosi Ase , Abenabo, Metemano | Selected community | * | * | * | * |  | 800,000.00 |  |  |  | * |  | MWD | Central Administration |
| Infrastructure Delivery and Management | Infrastructure Development | Complete Drilling and Construction of 10No. Boreholes (60-100m depth) with Hand Pump accessories and Platform construction Jato, Yokonor, Abomina Nkatekwan | Selection Communities | * | * | * | * |  | 500,000.00 |  |  |  | * |  | MWD | Central Administration |
| Infrastructure Delivery and Management | Infrastructure Development | Complete Repair and Maintenance of 12No. Boreholes (Mechanized/ Hand Pump) Municipality- wide | Municipality wide | * | * | * | * |  | 43,807.08 |  |  |  | * |  | MWD | Central Administration |
| Social Services Delivery | Education and Youth Development | Support to the organization of STMIE and SPAM | Municipality wide | * | * | * | * |  | 5,000.00 |  | 5,000.00 |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Organize "My First Day at School" in all 81 KG & Primary schools for 14387 pupils in the Municipal | Municipality wide | * | * | * | * |  |  |  |  |  |  |  | GES | Central Adm. |
| Infrastructure Delivery and Management | Infrastructure Development | Servicing of Municipal Education oversight committee meetings | Suhum | * | * | * | * |  |  |  | 5,000.00 |  |  |  | GES | Central Administration |
| Social Services Delivery | Education and Youth Development | Organize leadership training for all the 90 Basic School Heads | Municipality wide | * | * | * | * |  |  |  |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Provision of hygiene facilities in public schools | Municipality wide | * | * | * | * |  |  |  | 7,000.00 |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Independence Day celebration | Suhum | * | * | * | * |  |  | 80,000.00 |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Support to school enrolment drive | Municipality wide | * | * | * | * |  |  |  | 3,000.00 |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Construction of 1No. 3-Unit Classroom Block with Ancillary Facilities | Suhum Krobom |  |  |  |  |  |  | 677,653.00 |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Construction of 1No. 6-Unit Classroom Block with Ancillary Facilities | Praprababida-Sna |  |  |  |  |  |  | 850,000.00 |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Construction of 1No. 6-Unit Classroom Block with Ancillary Facilities at New Town | New Town | * | * | * | * |  | 1,350,000.00 |  |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Construction of 1No. 3-Unit JHS Classroom Block with Office, Store, Staff Common Room, 2unit Urinal and 4seater WC at Ayekotse | Ayekotse | * | * | * | * |  | 630,000.00 |  |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Construction of 1No. 3-Unit KG Classroom Block with Office, Store, Staff Common Room, 2unit Urinal and 4seater WC at Brong Densuso | Brong Densusu | * | * | * | * |  | 676,939.64 |  |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Construction of 1No. 3-Unit Classroom Block with Office, Store, Staff Common Room, 2unit Urinal and 4seater WC at Snah | Snah | * | * | * | * |  | 677,653.00 |  |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Construction of 1No. 6-Unit Classroom Block with Office, Store, Staff Common Room, 2unit Urinal and 4seater WC at Adarkwa | Adarkwa | * | * | * | * |  | 950,000.00 |  |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Construction of 1No. 3-Unit Classroom Block with Ancillary Facilities | Suhum Methodist JHS | * | * | * | * |  |  | 144,904.30 |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Complete the construction and payment of 1No. 3-unit classroom block with ancillary facilities | Suhum Densuso. | * | * | * | * |  |  | 121,995.80 |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Rehabilitation of Municipal Education Director Bungalow | Suhum | * | * | * | * |  | 38,055.60 |  |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Support to needy-but- brilliant students | Municipality wide | * | * | * | * |  | 77,954.24 |  |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | MP’s support to needy-but- brilliant students | Municipality wide | * | * | * | * |  | 20,000.00 |  |  |  |  |  | SUMA | Central Adm. |
| Social Services Delivery | Education and Youth Development | Complete Construction of 1No. 6-seater W/C and mechanized boreholes at Suhum M/A Primary School | Suhum M/A primary school. | * | * | * | * |  |  | 60,000.00 |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | C+D5 | Suhum | * | * | * | * |  | 950,000.00 |  |  |  | * |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Construction of 1NO.3 Unit Classroom Block with Office, Store, Staff Common Room, 2-Unit Urinal and 4-Seater W/C at Akorabo | Akorab | * | * | * | * |  | 600,000.00 |  |  |  | * |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Complete Construction of 1NO.3 KG and Nursery Classroom block with Office, Store, Servery and , 3-Seater W/C, 1No. at Kokooso | Kokooso | * | * | * | * |  | 643,807.08 |  |  |  | * |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Construction of 1No. 6-unit classroom block with ancillary facilities | Abenabo | * | * | * | * |  |  | 600,000.00 |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Procurement of 65No. Octagon Tables and Chairs for KG School – Metal Fabrication | Municipality wide | * | * | * | * |  | 260,000.00 |  |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Procurement of 800No. Mono Desks for JHS Schools – Metal Fabrication | Municipality wide | * | * | * | * |  | 1,203,333.00 |  |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Procurement of 740No. Dual Desks for Public Primary Schools – Metal Fabrication | Municipality wide | * | * | * | * |  | 1,040,625.00 |  |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Education and Youth Development | Procurement of 50No. Table and Chairs for Basic School Teachers | Municipality wide | * | * | * | * |  | 152,981.64 |  |  |  |  |  | GES | Central Adm. |
| Social Services Delivery | Health Delivery | Purchase of cleaning materials/sanitation / Covid 19 items. | Suhum | * | * | * | * |  | 20,000.00 |  | 30,000.00 |  | * |  | GHS | Central Adm. |
| Social Services Delivery | Health Delivery | celebrate Annual Child Health Promotion Week (CHPW) | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Conduct mop-ups for routine immunization and other child health services for children under 5 years, twice every year | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Construct 3 No.CHPS compounds with ancillary facilities at Abenabo, Adarkwa and Amanhyia |  | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Purchase basic medical equipment for service delivery (thermometer, BP apparatus, HB metres, etc) | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Celebrate World Breastfeeding Week. | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Celebrate Global Malaria Day, TB Day and HIV and AIDS Day | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Celebrate World Mental Health Awareness Month | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Hold Orientation training on leadership and management for Middle Line Managers | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Organize quarterly District Health Committee meetings | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Conduct Two sessions of safe motherhood training for midwives | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Hold a quarterly Public Health Emergency Management Committee meeting | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Renovate and retool health centres and CHPS compounds. These include Akorabo Health Centre, Kukua CHPS, Ntunkum CHPS, Nankese Health Centre, Suhum Health centre, Akote CHPS, Okanta CHPS |  | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Construction and Furnishing of 1No CHPS Compound with Maternity Block at Kromameng | Kromameng | * | * | * | * |  | 1,328,469.82 |  |  |  |  |  | GHS | Central Adm |
| Social Services Delivery | Health Delivery | Construction and Furnishing of 1No CHPS Compound with Maternity Block at Nankese Amanfrom Zongo | Nankese Amanfrom Zongo | * | * | * | * |  | 1,328,469.82 |  |  |  |  |  | GHS | Central Adm |
| Social Services Delivery | Health Delivery | Construct and equip Medical Laboratory Facilities for Akorabo, Nankese and Supresu Health Centres | Akorabo, Nankese Supresu | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Procure office equipment such as Air Conditioners, chairs, tables, laptops and computers, projectors, printers/Photocopiers, voltage stabilizers and lorry tyres | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Procure 4 No. motorbikes to support outreach service delivery | Suhum | * | * | * | * |  | 160,000.00 |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Refurbish the MHD vehicle to support health service delivery | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Celebrate Annual World Menstrual Hygiene Day | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Conduct Point Mass Distribution of Long-Lasting Insecticide Nets (LLINs) | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Hold quarterly Risk Communication and Community Engagement (RCCE) committee meetings | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Carry out Bi-Annual Stakeholder Engagement meetings on HIV/STI | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Renovate Municipal Health Directorate office | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Conduct quarterly Integrated supportive supervision to health facilities for coaching and on-the-job training | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Carry out periodic Performance Review Meetings with stakeholders | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Carry out operational research into emerging health threats in the municipality | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Intensify the implementation of Community Based Management of Malnourished cases at facilities | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Training and induction programmes for newly qualified health personnel | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Attend Regional level quarterly accounts validation meetings | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Organize Community Health Officers Training for CHOS | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Organize National and Sub National Immunization Days | Suhum | * | * | * | * |  |  |  |  |  |  |  | GHS |  |
| Social Services Delivery | Health Delivery | Celebrate Annual Child Health Promotion Week (CHPW) | Suhum | * | * | * | * | 18,000.00 |  |  |  |  | * |  | GHS | Central Adm. |
| Social Services Delivery | Health Delivery | Conduct mop ups for routine immunization and other child health services for children under 5years, twice every year | Suhum | * | * | * | * | 35,000.00 |  |  |  |  |  |  | GHS | Central Adm. |
| Social Services Delivery | Health Delivery | Celebrate Annual Child Health Promotion Week (CHPW) | Suhum | * | * | * | * | 18,000.00 |  |  |  |  | * |  | GHS | Central Adm. |
| Social Services Delivery | Health Delivery | Support to immunization and other public health outreach programmes | Municipality wide | * | * | * | * |  |  |  | 5,000.00 |  |  |  | GHS | Central Adm. |
| Social Services Delivery | Health Delivery | HIV/AIDS and roll back malaria programme | Municipaclity wide | * | * | * | * |  | 10,690.35 |  |  |  |  |  | GHS | Central Adm. |
| Social Services Delivery | Health Delivery | Organize municipal health committee meetings | Municipality wide | * | * | * | * |  |  |  | 5,000.00 |  |  |  | GHS | Central Adm. |
| Social Services Delivery | Health Delivery | Completion of 1No. CHPS compound with nurses’ quarters and mechanized borehole at Asarekrom | Asarekrom | * | * | * | * |  | 204,341.80 |  |  |  |  |  | GHS | Central Adm. |
| Social Services Delivery | Health Delivery | Complete Construction and Furnishing of 1. No CHPS compound with Maternity Block, Septic Tank, Dispensary, OPD, Laboratory, Consulting Room, Recovery Room, Two Bed room and Living Room Nurses Quarters at Akorabo | Akorabo | * | * | * | * | 1,096,903.54 |  |  |  |  |  |  | GHS | Central Adm |
| Social Services Delivery | Health Delivery | Completion of 1No. Health Facility at Kwabena Kumi | Kwabena Kumi | * | * | * | * |  | 200,000.00 |  |  |  |  |  | GHS | Central Adm |
| Social Services Delivery | Health Delivery | Complete Construction and Furnishing of 1. No CHPS compound with Maternity Block, Septic Tank, Dispensary, OPD, Laboratory, Consulting Room, Recovery Room, Two Bed room and Living Room Nurses Quarters at Abenabo | Abenabo | * | * | * | * | 1,096,903.54 |  |  |  |  |  |  | GHS | Central Adm |
| Social Services Delivery | social welfare &comm. dev | Procurement of Office Equipment | Municipality wide | * | * | * | * | 8,000.00 | 15,000.00 |  | 10,000.00 | 12,000.00 |  | * | Department of social | SUMA |
| Social Services Delivery | social welfare &comm. dev | CAPs review in 10 communities. | Municipality wide | * | * | * | * |  | 5,000.00 |  | 5,000.00 | 5,000.00 |  | * | Department of social | SUMA |
| Social Services Delivery | social welfare &comm. dev | Procurement of Office Supplies | Municipality wide | * | * | * | * | 2,000.00 | 3,000.00 |  | 2,000.00 | 2,000.00 |  | * | Department of social | SUMA |
| Social Services Delivery | social welfare &comm. dev | Mediate Forty (40) Case Work with Families | Municipality wide | * | * | * | * | 20,000.00 | 15,000.00 |  | 5,000.00 |  |  | * | Department of social | GPS,GHS,UNICEF, USAID |
| Social Services Delivery | social welfare &comm. dev | Facilitate the payment of LEAP Cash grants in 32 Communities bi-monthly | Municipality wide | * | * | * | * | 2,000.00 |  |  |  | 5,000.00 |  | * | Department of social | LMS,PFI,CFP |
| Social Services Delivery | social welfare &comm. dev | Update Municipal Disability Album on PWDs electronically | Municipality wide | * | * | * | * |  | 10,000.00 |  |  |  |  | * | Department of social | OPWD |
| Social Services Delivery | social welfare &comm. dev | Monitoring and Supervision of Organizations of Persons with Disability (OPWD) | Municipality wide | * | * | * | * |  | 2,500.00 |  |  |  |  |  | Department of social | SUMA, DFMC MEMBRES |
| Social Services Delivery | social welfare &comm. dev | Supervision of two (2) residential homes and reunification of children annually | Municipality wide | * | * | * | * | 3,000.00 |  |  | 2,000.00 | 2,000.00 |  | * | Department of social | SUMA, JR RHC & BASCO |
| Social Services Delivery | social welfare &comm. dev | Follow-up visits to 10 reunified children in RHCs | Municipality wide | * | * | * | * | 2,000.00 |  |  | 5,000.00 | 2,000.00 |  | * | Department of social | GHS, NGOs/CSOs |
| Social Services Delivery | social welfare &comm. dev | Monitor and Supervise fifty-five (55) Early Childhood Development Centres (ECDC) and train 22 Attendance | Municipality wide | * | * | * | * | 3,000.00 | 3,000.00 |  | 5,000.00 | 2,000.00 |  | * | Department of social | SUMA |
| Social Services Delivery | social welfare &comm. dev | Disbursement of Income Generating Items to 80 PWDs, 20 PWDs for Educational and Medical Support through the PWDs Share Disability Common Fund | Municipality wide | * | * | * | * |  | 300,500.00 |  |  |  |  |  | Department of social welfare | SUMA, GES, GHS, OPWDs |
| Social Services Delivery | social welfare &comm. dev | Monitor and Supervise individual PWD beneficiaries of the Disability Common Fund | Municipality wide | * | * | * | * |  | 8,000.00 |  |  |  |  | * | Department of social welfare | DFMC |
| Social Services Delivery | social welfare &comm. dev | Render Generic Services to 70 patients | Municipality wide | * | * | * | * |  | 3,000.00 |  | 2,000.00 | 2,000.00 |  | * | Department of social welfare | GHS, GPS |
| Social Services Delivery | social welfare &comm. dev | Sensitize and Improve 5 women groups in Local Economic Development and Bookkeeping. | Municipality wide | * | * | * | * |  | 10,000.00 |  |  | 3,000.00 |  | * | Department of social welfare | NBSSI, GEA |
| Social Services Delivery | social welfare &comm. dev | Extension Services in 10 communities. | 10 communities. | * | * | * | * | 2,000.00 |  |  |  |  |  | * | Department of social welfare | SOLIDARIDAD |
| Social Services Delivery | social welfare &comm. dev | Provide funds for monitoring visits to Day Care Centers, carry out routine visits to Court and Provide funds for Monitoring activities of parents and children as required by the children’s Act of 1998(Act 560) | Municipality wide | * | * | * | * | 2,000.00 |  |  | 5,000.00 |  |  |  | Department of social welfare | Central Adm. |
| Social Services Delivery | social welfare &comm. dev | Registration and Renewal of NHIS for 500 Indigent/Vulnerable Persons. | Municipality wide | * | * | * | * |  | 2,500.00 |  |  | 1,000.00 |  | * | Department of social | SUMA, NHIA, GES |
| Social Services Delivery | social welfare &comm. dev | Identification and Registration of Fifty (50) Persons with Disabilities (PWDs) | Municipality wide | * | * | * | * |  | 6,000.00 |  |  |  |  |  | Department of social. | SUMS,NHIA,OPWDS, GHS |
| Social Services Delivery | social welfare &comm. dev | Sensitize women and girls on teenage pregnancy | Municipality wide | * | * | * | * | 1,000.00 |  |  | 1,000.00 |  |  |  | Community Dev. | Central Adm. |
| Social Services Delivery | social welfare &comm. dev | Train School Feeding caterers on nutrition and food hygiene | Municipality wide | * | * | * | * |  |  |  | 1,000.00 |  |  |  | MHD | Central Adm. |
| Social Services Delivery | social welfare &comm. dev | Preparing and submit Social Enquiry Reports to the Juvenile court and Family Tribunal | Municipality wide | * | * | * | * | 2,000.00 |  |  | 3,000.00 |  |  | * | Department of social welfare | JS, GPS |
| Social Services Delivery | social welfare &comm. dev | Sensitize communities and civil society organizations on the right of the child/ organize women groups to undertake income generating activities. | Municipality wide | * | * | * | * | 7,000.00 |  |  | 5,000.00 |  |  |  | Department of social welfare | Central Adm. |
| Social services delivery | social welfare &comm. dev | Organize and Prepare CAPS in 10 Communities | Municipality wide | * | * | * | * | 4,000.00 | 5,000.00 |  |  |  |  | * | Department of social welfare | NCCE, ISD, NGOs, CSOs |
| Social services delivery | social welfare &comm. dev | Organize home visit program in Ten (10) communities | Municipality wide | * | * | * | * | 4,000.00 | 3,000.00 |  |  |  |  | * | Department of social welfare | NCCE, ISD |
| Social services delivery | social welfare &comm. dev | Sensitization On Child Protection in 20 Communities | Municipality wide | * | * | * | * | 10,000.00 | 15,000.00 |  |  | 6,000.00 |  | * | Department of social welfare | NCCE, CHRAJ, GES, L. DEPT |
| Social services delivery | social welfare &comm. dev | Sensitize 10 groups in the Municipality on Child Protection Issues. | Municipality wide | * | * | * | * |  | 5,000.00 |  | 5,000.00 | 1,000.00 | * |  | Department of social welfare | NCCE, CHARJs |
| Social services delivery | social welfare &comm. dev | Establish Community Child Protection Communities in 10 Communities | Municipality wide | * | * | * | * |  | 10,000.00 |  |  | 3,000.00 | * |  | Department of social welfare | NGOs & CSOs |
| Social services delivery | social welfare &comm. dev | Foster Care Drive in 30 Churches and Mosques, 10 with Focus Groups | Municipality wide | * | * | * | * | 2,000.00 |  |  | 5,000.00 | 2,000.00 | * |  | Department of social welfare | LCC, NGOs/CSOs |
| Social services delivery | social welfare &comm. dev | Case Management Issues and Follow-Up | Municipality wide | * | * | * | * | 4,000.00 |  |  | 20,000.00 | 2,000.00 | * |  | Department of social welfare | GHS GES MA NGOs |
| Environmental Sanitation and Management | Disaster prevention and management | Carry out sanitation improvement activities | Municipality wide | * | * | * | * |  |  |  | 100,000.00 |  |  |  | MEHO | Central Adm. |
| Environmental and sanitation and management | Disaster prevention and management | Established post |  |  |  |  |  | 604,261.56 |  |  |  |  |  |  | EDP | Central Admin |
| Infrastructure and delivery management | Infrastructure Development | Purchase of sanitary tools | Suhum | * | * | * | * |  | 1,000,000.00 |  | 40,000.00 |  | * |  | MEHU | Central Administration |
| Environmental Sanitation and Management | Disaster prevention and management | Desilting and dredging works | Municipality wide | * | * | * | * |  | 100,000.00 |  |  |  |  |  | MEHO | Central Adm. |
| Environmental Sanitation and Management | Infrastructure Development | Procure and allocate 10No. metal containers | Municipality wide | * | * | * | * |  | 220,000.00 |  |  |  | * |  | MEHO | Central Adm. |
| Environmental Sanitation and Management | Infrastructure Development | Evacuation of Refuse Dump and Maintenance of Final Dumping Site | Municipality wide | * | * | * | * |  | 200,000.00 |  |  |  | * |  | MEHO | Works Dept. |
| Environmental Sanitation and Management | Infrastructure Development | Conduct sensitization programs on sanitation and hygiene | Municipality wide | * | * | * | * |  | 60,000.00 |  | 20,000.00 |  | * |  | MEHO | Central Administration |
| Environmental Sanitation and Management | Infrastructure Development | Sensitize community and household on the need to conduct domestic toilets | Municipality wide | * | * | * | * |  | 30,000.00 |  | 30,000.00 |  | * |  | MEHO | Central Administration |
| Environmental Sanitation and Management | Infrastructure Development | Provide technical assistance in the construction of household toilets | Municipality wide | * | * | * | * |  | 60,000.00 |  |  |  | * |  | MEHO | Works Dpt |
| Environmental Sanitation and Management | Infrastructure Development | Manual dislodgement of caked/choked public toilets | Municipality wide | * | * | * | * |  | 450,000.00 |  | 50,000.00 |  | * |  | MEHO | Works Dpt |
| Environmental Sanitation and Management | Infrastructure Development | Carry out regular evacuation of communal containers | Municipality wide | * | * | * | * |  | 650,000.00 |  |  |  |  |  | MEHO |  |
| Environmental Sanitation and Management | Infrastructure Development | Screen Food Vendors | Municipality wide | * | * | * | * |  |  |  | 50,000.00 |  |  |  | MEHO |  |
| Environmental Sanitation and Management | Infrastructure Development | Procure and allocate working uniforms for sanitary workers (EHO, EHAs, Labourers) | Municipality wide | * | * | * | * |  | 60,000.00 |  | 30,000.00 |  | * |  | MEHO | Central Administration |
| Environmental Sanitation and Management | Infrastructure Development | Place/Locate Litter Bins at Vantage Ares | CBD | * | * | * | * |  | 200,000.00 |  |  |  |  |  | MEHO | Central Administration |
| Environmental Sanitation and Management | Infrastructure Development | Complete Construction 2 Institutional Public Toilet / Urinals | Selected School | * | * | * | * |  | 200,000.00 |  |  |  | * |  | MEHO | Works Dpt |
| Environmental Sanitation and Management | Infrastructure Development | Undertake District wide Fumigation Exercise | Municipality wide | * | * | * | * |  | 418,600.00 |  |  |  | * |  | MEHO | Works Dept. |
| Environmental Sanitation and Management | Infrastructure Development | Regular desilting of all chocked drains | Municipality wide | * | * | * | * |  | 360,000.00 |  |  |  | * |  | MEHO | Works Dept. |
| Environmental Sanitation and Management | Infrastructure Development | To carry out monthly, domiciliary inspections in communities |  | * | * | * | * |  |  |  | 30,000.00 |  | * |  | MEHO |  |
| Environmental Sanitation and Management | Infrastructure Development | Organize National Sanitation Day (Clean Up Exercise) |  | * | * | * | * |  | 200,000.00 |  |  |  | * |  | MEHO | Works Dept. |
| Environmental Sanitation and Management | Infrastructure Development | To organize stray animals control/arrest in all the 4 zonal council |  | * | * | * | * |  |  |  | 30,000.00 |  |  |  | MEHO |  |
| Environmental Sanitation and Management | Infrastructure Development | To carry out quarterly monitoring and supervision visit |  | * | * | * | * |  |  |  | 20,000.00 |  |  |  | MEHO |  |
| Environmental Sanitation and Management | Infrastructure Development | Regular Dislodging of all institution and public toilet | Municipality wide | * | * | * | * |  | 386,957.08 |  |  |  |  |  | MEHO | MWD |
| Environmental Sanitation and Management | Infrastructure Development | Monitoring and Supervision of Enviro9nmental Service Providers | Municipality wide | * | * | * | * |  | 10,000.00 |  |  |  | * |  | MEHO | SUMA |
| Environmental Sanitation and Management | Infrastructure Development | Conduct sensitization on WASH activities | Municipality wide | * | * | * | * |  | 10,000.00 |  |  |  |  |  | MEHO | SUMA |
| Environmental Sanitation and Management | Infrastructure Development | Procure 2 No Tricycles | Municipality wide | * | * | * | * |  | 80,000.00 |  |  |  |  |  | MEHO | SUMA |
| Environmental Sanitation and Management | Infrastructure Development | Complete the construction of 1 No. Slaughter house at Suhum | Municipality wide | * | * | * | * |  | 600,000.00 |  |  |  |  |  | MEHO | SUMA |
| Environmental Sanitation and Management | Disaster prevention and management | Sanitation Improvement Package (SIP) and fumigation | Municipality wide | * | * | * | * |  | 523,250.00 |  |  |  |  |  | NADMO | SuMA |
| Environmental Sanitation and Management | Disaster prevention and management | To undertake (600) public education in communities, schools, Mosques, Churches, Market and Organized groups, on the need to prevent disasters in the Municipality |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | To identify (120) Community hazards and providing mitigation measures to reduce disasters. |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | Inspection of Fuel/Gas Stations, Alcohol Distillers and High Risk Businesses for the identification, and assessment of hazards to prevent disasters |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | To dredge (8) major drains that are flood prone in the municipality |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | To undertake (20) road safety education to ensure drivers/Motor riders adhere to road safety regulations to reduce road accidents in the Municipality |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | To provide relief items to 400 Disaster Victims to reduce their plight. |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | The activity is planned to train (33) NADMO staff, and (3) Disaster Volunteer Groups on how to provide first line response in the event of disasters. |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | The activity seeks to train (25) DVG's on best farming practices to help them in their Income Generating Activities |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | The activity seeks to train (30) NADMO Staff to build the capacity of staff to execute their duties efficiently. |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | To plant 3000 trees seedlings to serve as wind breaks and also mitigate the excessive effects of climate change within the municipality |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | The activity will take the form of crop farming and raising of tree and crop nurseries to serve as motivation for the group members. |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | The activity is planned to mark the International Day for Disaster Reduction which is marked every 13th October. |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | The activity is planned to help the secretariat plan, implement and monitor disaster prevention and management activities in the municipality. |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | To undertake (700) public education in Communities, Schools, Mosques, Churches, Markets and Organized groups, on the need to prevent disasters in the Municipality |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | To identify (160) Community hazards and providing mitigation measures to reduce disasters. |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | To provide relief items to 500 Disaster Victims to reduce their plight. |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | To plant 3500 trees seedlings to serve as wind breaks and also mitigate the excessive effects of climate change within the municipality |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | To undertake (800) public education in Communities, Schools, Mosques, Churches, Markets and Organized groups, on the need to prevent disasters in the Municipality |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | To identify (200) Community hazards and providing mitigation measures to reduce disasters. |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | To provide relief items to 600 Disaster Victims to reduce their plight. |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | To plant 4000 trees seedlings to serve as wind breaks and also mitigate the excessive effects of climate change within the municipality |  | * | * | * | * |  |  |  |  |  |  |  | NADMO |  |
| Environmental Sanitation and Management | Disaster prevention and management | Provision of relieve items/ organize public education on climate change/bushfires and flood and World Disaster Day celebration in the municipality. | Municipality wide | * | * | * | * |  | 60,000.00 |  | 20,000.00 |  |  |  | NADMO | SuMA |
| Environmental Sanitation and Management | Disaster prevention and management | Provide for CC-DRR activities | Municipality wide | * | * | * | * |  | 20,000.00 |  | 10,000.00 |  |  |  | NADMO | SuMA |
| Environmental Sanitation and Management | Disaster prevention and management | Support Disaster Related activities and Intervention. | Municipality wide | * | * | * | * |  | 40,000.00 |  |  |  |  |  | NADMO | SuMA |
| Environmental Sanitation and Management | Disaster prevention and management | Undertake National Tree for Life Planting Exercise. | Municipality wide | * | * | * | * |  | 20,000.00 |  | 3 |  | * |  | NADMO | PPD SuMA |
| Infrastructure delivery and Management | Infrastructure Development | Installation, marking and maintenance of road furniture along selected roads | Suhum | * | * | * | * |  |  |  |  |  |  |  | UR | Central Adm. |
| Economic Development | Trade, Tourism Industrial Dev. | Provide business coaching services to entrepreneurs (WIDU) | Municipality wide | * | * | ,* | * |  |  |  | 2,000.00 |  |  |  | GEA | SuMA |
| Economic Development | Trade, Tourism Industrial Dev. | Carry out Business Counselling | Municipality wide | * | * | * | * |  |  |  | 2,000.00 |  |  |  | GEA | SuMA |
| Economic Development | Trade, Tourism Industrial Dev. | Organize financial literacy training for Dressmakers and Beauticians | Municipality wide | * | * | * | * |  |  |  | 2,000.00 |  |  |  | GEA | SuMA |
| Economic development | Trade, Tourism and Industrial Dev | Assistance in formalization of business in the informal sector to take advantage of government support packages | Municipality wide |  |  |  |  |  |  |  | 5,000.00 |  |  |  | GEA | SuMA |
| Economic Development | Health Delivery | Assembly’s contribution to local economic development (vocational training for the youth) | Suhum | * | * | * | * |  | 100,000.00 |  | 100,000.00 |  |  |  | GEA | Central Adm. |
| Economic Development | Trade, Tourism Industrial Dev. | Undertake Kaisen activities | Municipality wide | * | * | * | * |  |  |  | 2,000.00 |  |  |  | GEA | SuMA |
| Economic Development | Trade, Tourism Industrial Dev. | Support SMEs in agro-processing (Gari, Palm Oil and Vegetable production | Municipality wide | * | * | * | * |  |  |  | 30,000.00 |  |  |  | GEA | SuMA |
| Economic Development | Trade, Tourism Industrial Dev. | Conduct training session for 15 women in alternative livelihood | Municipality wide | * | * | * | * |  |  |  | 30,000.00 |  |  |  | GEA | SuMA |
| Economic Development | Trade, Tourism Indus. | Promote aquaculture development | Municipality wide | * | * | * | * |  |  |  | 30,000.00 |  |  |  | GEA | SuMA |
| Economic Development | Trade, Tourism Industrial Dev. | Assist SMEs to register their businesses | Municipality wide | * | * | * | * |  |  |  | 15,000.00 |  |  |  | GEA | SuMA |
| Economic Development | Trade, Tourism Industrial | Complete Construction of Industrial Workshop | Suhum | * | * | * | * |  | 200,000.00 |  |  |  |  |  | GEA | MWD |
| Economic Development | Trade, Tourism Industrial |  | Suhum | * | * | * | * |  | 200,000.00 |  |  |  |  |  | GEA | MWD |
| Economic Development | Trade, Tourism Industrial | Construction of 1 No. 8-unit lockable stores with 10-unit open market shed at Akorabo | Akorabo | * | * | * | * |  | 700,000.00 |  |  |  |  |  | GEA | MWD |
| Economic Development | Infrastructure Development | Construction of 24Hour Economic Market (Multi- Purpose Story Lockable Stores) | Suhum | * | * | * | * |  | 5,484,517.69 |  |  |  |  |  | Central Admin | MWD |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GRAND TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |